- Procurement plan

| Programme Component or Project Ref. No | Contract Name | Non-objection by CH | Tender announcement in CH | English translation of tender documents for bidders | If applicable, planned deadline for submitting documentation to Swiss "non objection" | Launch of tender planned | Tender notice will be submitted to Swiss side before publication | English translation of tender documents will be made available to bidders | Actual launch of tender (publication of tender notice) | Contract signature planned | Actual contract signature | Contract completion planned | Actual contract completion | Initially estimated costs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | quarter / year | quarter / year | yes/no | yes/no | date | quarter / year | date | quarter / year | date | EUR | CHF |
| Strengthening the social- and child protection services | Advertising new possibilities and positive changes in social care- and child protection studies and work environment |  |  |  |  | III-IV Q 2024 |  |  |  | I - II Q 2025 |  | II Q of 2026 |  | 400,000 |  |
| Cultural and linguistic integration | Development and implementation of new digital tools |  |  |  |  | IV Q of 2025-I Q 2026 |  |  |  |  |  |  |  | 800,000 |  |
| Cultural and linguistic integration | Development and piloting a volunteer programme |  |  |  |  | II Q 2025- IIII Q 2025 |  |  |  |  |  |  |  | 220,000 |  |
| Cultural and linguistic integration | Development and providing activities to introduce Estonian cultural space and increase social connections |  |  |  |  | I-II Q 2025 |  |  |  |  |  |  |  | 700,000 |  |
| Cultural and linguistic integration | Development and providing activities to introduce Estonian cultural space and increase social connections |  |  |  |  | III-IV Q 2026 |  |  |  |  |  |  |  | 700,000 |  |