## Leht1
Monitoring plan for EE-CLIMATE Programme 2024
Project # | Project name | Monitoring Action | Planned timing (Q) | Criteria for Monitoring (especially for site visits) | Risk issue with the project (if applicable) | Comments
EE-CLIMATE-0026 | Climate change mitigation and adaptation activities in Viljandi town | On-site visit | II | Verification of costs (to see if construction works have been completed as stated in documents) | NA | once per poject implementation
EE-CLIMATE-0022 | Close-to-nature solutions at Keila Song Festival Grounds | On-site visit | II | Verification of costs (to see if construction works have been completed as stated in documents) | NA | once per poject implementation
EE-CLIMATE-0020 | Construction of Drinking Water Taps | On-site visit | II | Verification of costs (to see if construction works have been completed as stated in documents) | NA | once per poject implementation
EE-CLIMATE-0023 | Climate change adaptation activities in Kohtla-Järve | On-site visit | II | Verification of costs (to see if construction works have been completed as stated in documents) | NA | once per poject implementation
EE-CLIMATE-0024 | The Pelgu allotment garden construction and follow-up activities in urban gardening | On-site visit | II | Verification of costs (to see if construction works have been completed as stated in documents) | NA | once per poject implementation
EE-CLIMATE-0018 | Establishment of a rainwater recovery system in the Metsanurga area | On-site visit | II | Verification of costs (to see if construction works have been completed as stated in documents) | Delays in activities | once per poject implementation
EE-CLIMATE-0015 | Circular Economy project in Rae Municipality | On-site visit | II | Verification of costs (to see if pilot area has been developed) | NA | once per poject implementation
EE-CLIMATE-0025 | Creating a Pernova Climate Education demonstration area "Smart Park" /Pernova kliimahariduse näidisala "" SMART PARK" loomine | On-site visit | II | Verification of costs (to see if construction works have been completed as stated in documents) | NA | once per poject implementation
EE-CLIMATE-0016 | Climate change education to promote climate action | On-site training day visit | II | Check the training day if it is organized as stated (beneficiaries, teaching methods, etc) | NA
EE-CLIMATE-0014 | The transition of civic amenity sites into reuse and repair centres | On-site visit | II | Verification of costs (to see if Paljassaare workshop has been completed as stated in documents) | NA | once per poject implementation
EE-CLIMATE-0017 | CIRCULAR RENOVATION IN TARTU | On-site visit | I | Verification of costs (to see if works have been completed as stated in documents) | NA | once per poject implementation