## List of activities
| List of activities | 2025 | [11 empty] | 2026 | [11 empty] | 2027
Project | Enhancing and Aligning the Competency Standards of Ukrainian Prison Officers with European Standards
Project code | 8VS1-VM-UA-JUMV25
Project period | 01.04.2025 – 30.11.2027
| Outcome/Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Outcome 1: An initial training curriculum adapted for Ukrainian prison officers has been developed, based on the best practices of Europe and Estonia.
Activity 1.1 | Study visit to Ukraine (EST 10 people)
Activity 1.2 | Visit to Estonia – Training seminar (UA 8 people)
Activity 1.3 | 10-day special program at the Estonian Academy of Security Sciences (UA 10 people)
Activity 1.4 | 5-day practical training in an Estonian prison
Activity 1.5 | 5-day seminar at the Estonian Academy of Security Sciences: Working with the initial training curriculum
Activity 1.6 | Ukrainian partners continue working independently on the curriculum
Activity 1.7 | Visit to Ukraine (EST 3 people) – supporting the further development of the work done independently by Ukrainian partners.
Activity 1.8 | Visit to Ukraine and training seminar (EST 8 people) – Presentation/overview of the finalized curriculum and learning materials, and strategy for implementing the new curriculum.
Outcome 2: Study materials adapted to the needs and expectations of the target group have been developed for prison officers.
Activity 2.1 | Work with the book "Core Correctional Skills": rights and translation of the book into Ukrainian
Activity 2.2 | 5+2-day training seminar in Estonia + virtually and/or in Ukraine ("Core Correctional Skills" training - Ioan Durnescu) (UA 10 people)
Activity 2.3 | Editing and printing of learning material, followed by sending/shipping to Ukraine
Activity 2.4 | Creation of an interactive digital textbook based on the learning materials (to support independent learning and reinforcement of knowledge)
Activity 2.5 | Visit to Ukraine (EST 8 people) – A training seminar/opening seminar organized by the Ukrainian partner to introduce the completed learning materials to Ukrainian prison officers
Outcome 3: A mentorship and practical training system supporting the initial training curriculum has been developed.
Activity 3.1 | 5-day training seminar in Ukraine (including formation of a working group) (EST 5 people)
Activity 3.2 | 5-day work of Estonian expert in Ukraine based on the input and support of the working group – preparing a guide for the mentoring and practical system
Activity 3.3 | Visit to Estonia – Training seminar (UA 8 people)
Activity 3.4 | Translation and editing of the manual into Ukrainian.
Activity 3.5 | 5-day training seminar at the Estonian Academy of Security Sciences "Training Of Trainers" and prison practice (UA 10 people)
Activity 3.6 | Visit to Ukraine (EST 2 people): Trainers will conduct a trainer training session with the support of the Estonian expert.
Outcome 4: Prison officers have successfully completed in-service training at the Estonian Academy of Security Sciences and in an Estonian prisons.
Activity 4.1 | 10-day training program at the Estonian Academy of Security Sciences (UA 10 people)
Activity 4.2 | 10-day practical training in an Estonian prison
Activity 4.3 | Visit to Estonia – Training seminar/feedback session (UA 8 people)
Activity 4.4 | Summary visit to Ukraine (EST 8 people)
Monitoring and reporting
Activity 1. | Project progress report and evaluation | bar: 1 Jan; 7 Jul; 1 Jan; 7 Jul
Activity 2. | Project summary and submission of the final report | bar: 12 Dec
Communication activities
Activity 1. | Announcement of the project’s first operational activities | bar: 5 May
Activity 2. | Sharing project activities on social media with image and caption | bar: 6 Jun; 10 Oct; 6 Jun; 11 Nov; 6 Jun
Activity 3. | Final communication activities about the project’s end and results | bar: 12 Dec