## Procurement plan
Procurement Plan
To be filled in by Programme Operator
Programme Component or Project Ref. No | Contract Name | If applicable, planned deadline for submitting documentation to Swiss "non objection" | Launch of tender planned | Tender notice will be submitted to Swiss side before publication | English translation of tender documents will be made available to bidders | Actual launch of tender (publication of tender notice) | Contract signature planned | Actual contract signature | Contract completion planned | Actual contract completion | Initially estimated costs |  | Actual costs based on signed contracts |  | Contractor | Expenditures incurred based on signed contracts |  | Comments
|  | quarter / year | quarter / year | yes/no | yes/no | date | quarter / year | date | quarter / year | date | EUR | CHF | EUR | CHF | name | EUR | CHF | status/ appeals/ cancelling or repetion of tender (incl. reason)/ numbers of bidders and rejected bids/risks/ irregularities related to the tender/ difficulties with the the Contractor/ suspension of works etc.
Programme Component 1 “Cultural and linguistic integration” | Development and implementation of new digital tools (II) | I/2026 | I/2026 | yes | no |  | II/2026 |  | II/2027 | EUR: 200000; CHF: 207216
Programme Component 1 “Cultural and linguistic integration” | Development and implementation of new digital tools (III) | III/2026 | III/2026 | yes | no |  | I/2027 |  | IV/2027 | EUR: 300000; CHF: 310824
Programme Component 1 “Cultural and linguistic integration” | Development and implementation of new digital tools (IV) | IV/2026 | IV/2026 | yes | no |  | II/2027 |  | I/2028 | EUR: 300000; CHF: 310824
Programme Component 1 “Cultural and linguistic integration” | Development and piloting a volunteer programme | III/2025 | IV/2025 | yes | no |  | IV/2025 |  | I/2027 | EUR: 220000; CHF: 227938
Programme Component 1 “Cultural and linguistic integration” | Development and implementation of activities introducing Estonian culture and customs space | II/2025 | II/2025 | yes | no |  | III/2025 |  | IV/2026 | EUR: 650000; CHF: 673453
Programme Component 1 “Cultural and linguistic integration” | Development and providing activities to introduce Estonian cultural space and increase social connections | III/2026 | III/2026 | yes | no |  | IV/2026 |  | I/2028 | EUR: 575000; CHF: 595747
Programme Component 2 "Strengthening the social-and child protection services" | Advertising new possibilities and positive changes in social care- and child protection studies and work environment | II/2026 | II/2026 | yes | no |  | IV/2026 |  | I/2028 | EUR: 373000; CHF: 386458
Programme Component 3 “Increasing multicultural competence in the education sector” | No procurements of this amount are planned
Programme Component 4 “Strengthening civil society through social innovation” | No procurements of this amount are planned
<
Note on A5: Provide an overview over all the procurements related to the SM. In case of Programmes, structure the table according to Programme Components. Unless otherwise agreed with Switzerland, only procurments above the threshold of CHF 150 000 must be listed. Insert a number. For related tenders use the same number and distinguish them using additional letters. For example, in case of a building renovation, there will be related tenders such as the technical project of the renovation (1a),the supervision of the renovation works (1b) and the renovation works (1c). The table is to be gradually updated and completed on a half-yearly basis.