## Monitoring Plan
Annex 7A 1
Monitoring Plan
Type of monitoring | Level of monitoring |  |  |  | Monitoring topic | Planned timing | Reponsible authority | Parties involved
| Swiss-Estonian Cooperation programme | SM "Biodiversity Programme" | SM "Supporting Social Inclusion" | Project
Risk assessment of the Cooperation Programme | yes |  |  |  | The risks related to the cooperation programme are assessed by POs, PCOs (only ministries) and the NCU. The NCU consolidates the results of the risk assessment and prepares a risk assessment table with risk mitigation measures. The implementation of mitigation measures is monitored to ensure their timely implementation. | once a year | NCU | Programme Operators PCOs (only ministries)
Risk assessment of projects in SFOS |  |  |  | yes | A separate project is opened in SFOS for each PO, PCO, implementer, and for the Technical Assistance. A risk assessment is carried out for each project. Based on the result of the risk assessment, the sample for checking the expense documents and sample for on-the spot controls are formed. Once a year, the results of controls, detected irregularities, observations made in audit reports are analysed, and depending on the results, the need for a new risk assessment of the project is decided. Upon need, the risk assessment of the project is carried out. | once a year | NCU
On-the-spot controls |  |  |  | yes | The need for on-the-spot controls is determined based on the project's risk analysis. At the time of submitting the Annual Cooperation Programme Report, no on-the-spot controls are foreseen in 2025 based on the risk analysis. Project risks will be reassessed in 2026, and the need for on-the-spot controls will be determined accordingly. |  | NCU
Monitoring missions/monitoring visits |  | yes | yes |  | Monitoring missions, as described in the Regulations for monitoring progress towards outputs and outcomes according to agreed indicators, baselines, and targets, are not planned. Progress can be monitored through Annual Support Measure Reports, RRs, and meetings of the SC and Task Force. Joint meetings and visits involving the NCU and SCO, together with the PO, PCO, implementers, partners, held alongside the SC and/or Annual Meetings, may conditionally be referred to as monitoring visits. These meetings and visits provide an opportunity to examine more closely the activities of the PCO, implementer or partner within the programme component. | SM "Supporting Social Inclusion" 17.02.2025 -National Foundation of Civil Society, Viljandi 18.06.2025 National Library SM "Biodiversity Programme" 14.06-16.06.2025 Saaremaa | NCU SCO | POs, PCOs, implementers, partners
Annual check of payment processing deadlines | yes |  |  |  | Annual check of payment processing deadlines is carried out on the basis of information system SFOS report and concerning all programmes and projects. If payment deadlines are exceeded, the reasons are identified. | once a year | NCU
Annual check of irregularity processing deadlines | yes |  |  |  | Annual check of irregularity processing deadlines is carried out on the basis of information system SFOS report and concerning all programmes and projects. If irregularity processing deadlines are exceeded, the reasons are identified. | once a year | NCU
Performance analysis | yes |  |  |  | The performance analysis assesses the functioning of the system of every aspect of the implementation (payments, eligibility, financial corrections, irregularities, audits, etc). | once a year | NCU
Annual Cooperation Programme Reports | yes |  |  |  | Annual Cooperation Programme Reports provide an overview of the progress of the cooperation programme – including the implementation of support measures, management, audits, irregularities, achievement of indicators, and other relevant aspects. | once a year by the end of April | NCU | POs, PCOs, implementers
Annual Support Measure Reports |  | yes | yes |  | Annual Support Measure Reports provide an overview of the progress of the support measure – implementation, management, outputs, outcomes, achievement of indicators and other aspects. | once a year by the end of March | POs | POs, PCOs, implementers, NCU
Reimbursement requests |  | yes | yes |  | Reimbursement requests provide an overview of the expenses incurred and activities conducted under the support measure during the previous 6 months. | twice a year by the end of March by the end of September | 1) Support Measures -POs 2) Technical Assistance Fund - NCU | 1) PCOs, implementers,
Annual meetings | yes |  |  |  | During the meetings, progress of the cooperation programme is assessed, risks are discussed, the milestones for the upcoming year are presented, the annual cooperation programme report is discussed and approved and decisions regarding the overall cooperation programme are made. | once in a year | NCU | SCO, representatives of Switzerland
Support Measure Steering Committee |  | yes | yes |  | SM Steering Committee supervises the progress of implementation of the support measure, makes decisions regarding the support measure and approves modifications of the support measure. | meets at least once in a year | POs | SCO, NCU, PCOs, implementers
Task Force meetings |  | yes | yes |  | Task Force monitors the implementation of the support measure and components on an ongoing basis, proposes modifications to the Steering Committee. | meets twice in a year | POs | PCOs, NCU, implementers For the "Biodiversity Programme" also SCO

## Evaluation Plan
Annex 7B 1
Evaluation Plan
Programme information | [6 empty] | Evaluation Information
Title | Support Measure Type | Executing Agency | Objective | Thematic Area | Duration (starte/end) | Requested Swiss contribution (CHF) | Budget (CHF) | Type of Evaluation | Evaluation Objectives (reasons and learning goals) | Timing | Data needs and collection methods (eports, interviews, surveys, other) | Knowledge Sharing (Who will benefit from the evaluation? How will findings be shared?)
Biodiversity Programme | Programme | Ministry of Climate | Protecting the environment and the climate | Nature conservation and biodiversity | 01.05.2024-31.08.2024 | 6 930 000 | 55 0000 (including VAT) | Ex-post evaluation of the programme | The following aspects are planned to be evaluated: *Effectivesess, impact/predicted impact of the programme *Achievement of outcomes of the programme *Lessons learned Additionally, positive changes initiated with the support of the programme could be identified. | In 2028 (January-August) | Qualitative and quantitative methods (e.g reports, interviews etc) can be used. The best methodology for carrying out the evaluation shall be provided by the tenderer. | The beneficiaries are: the programme operator, component operators, policy makers; donor; general public. The results can be used while preparing strategies and new programmes. Evaluation report will be availaible for the general public.
Supporting Social Inclusion | Programme | Ministry of Culture | Managing migration and supporting integration. Increasing public safety | Providing support to migration management and promoting integration measures | 01.06.2024-31.08.2024 | 18600000 | 55 0000 (including VAT) | Ex-post evaluation of the programme | The following aspects are planned to be evaluated: *Effectiveness, impact/predicted impact of the programme *Achievement of outcomes of the programme *Lessons Learned Additionally, positive changes initiated with the support of the programme could be identified. | In 2028 (January-August) | Qualitative and quantitative methods (e.g reports, interviews etc) can be used. The best methodology for carrying out the evaluation shall be provided by the tenderer. | The beneficiaries are: the programme operator, component operators, policy makers; donor; general public. The results can be used while preparing strategies and new programmes. Evaluation report will be availaible for the general public.