## Reimbursement Request
Swiss-Estonian Cooperation Programme
Reimbursement Request No. 1
Bio-Diversity Programme
Instructions |  |  |  |  | Estonia
A. Basic information
Support Measure Title | Bio-Diversity Programme
Support Measure Identification Code |  |  |  |  | 7F-10768.01
Support Measure duration | from | 2024-05-01 |  | to | 2028-08-31
Name of Executing Agency (EA)
Reporting period | from | 2024-05-01 |  | to | 2025-06-30
Reimbursement Request No | 1
Total Support Measure Budget (local currency) | 8447107 |  |  | EUR
Maximum Swiss contribution (CHF) | 6930000 |  | CHF
Swiss co-financing rate | on total budget |  | 85% | on total expenditures |  | 85%
Exchange rate used | CHF/EUR | 1 |  | Date of exchange rate
B. Amount requested by the Paying Authority
Total amount requested | 669862.51 |  |  | EUR | 669862.51 | CHF
National co-financing | 100479.37 |  |  | EUR | 100479.37 | CHF
Deductions (according to Regulations 11.4/3) | 0 |  |  | EUR | 0 | CHF
Swiss co-financing = Reimbursement by CH | 569383.14 |  |  | EUR | 569383.14 | CHF
C. Available amount from the Swiss Contribution
Maximum Swiss Contribution | 6930000 |  |  | CHF | 100%
Cumulative amount received from Switzerland | 0 |  |  | CHF | 0%
Available amount before the current reimbursement | 6930000 |  |  | CHF | 100%
Total amount of current reimbursement request | 569383.14 |  |  | CHF | 8.22%
Remaining amount after the current reimbursement | 6360616.86 |  |  | CHF | 91.78%
D. Certification and approval of Reimbursement Request
Executing Agency: Programme Operator
Name of the institution: Ministry of Climate
Address:Suur-Ameerika 1, 10122 Tallinn, Estonia
Name of the contact person: Kairi Toiger
Position: Advisor, financial department
Email: kairi.toiger@kliimaministeerium.ee
Phone number: +372 6262 931
The Executing Agency hereby certifies
(i) that the Support Measure is implemented in accordance with the Support Measure Agreement and Support Measure Implementation Agreement; (ii) the reporting under Physical Progress, Financial Progress and Procurement Plan is true and accurate; (iii) that the reporting under Financial Progress reflects correctly the incurred expenditures; (iv) that recoverable VAT is not included in the Financial Progress as eligible expense; (v) that no double-financing occurs; (vi) that all procurements for which expenditures were incurred during the reporting period have been conducted in compliance with the applicable law of the Partner State and EU directives on public procurement.
Name: Marten Kokk | Position: | Secretary General
Place, date and signature | digitally signed
National Coordination Unit
Name of the institution: | State Shared Service Centre
Address: | Lõkke 4, 10122 Tallinn
Name of the contact person: | Helena Musthallik
Position: | programme expert
Email: | helena.musthallik@rtk.ee
Phone number: | +37256466003
The National Coordination Unit hereby certifies
(i) that the information and financial data provided in this Reimbursement Request has been thoroughly reviewed and found to be correct, reliable and accurate; (ii) that claimed expenditures are incurred as part of the Support Measure in accordance with the Framework Agreement, the relevant Support Measure Agreement and Support Measure Implementation Agreement; (iii) that all payments declared have actually been made in the indicated (or exceptionally previous) reporting period. (iv) the compliance with state aid rules of all activities performed in the reporting period.
Name: Urmo Merila | Position: | Deputy Director General
Date and signature | digitally signed
Paying Authority
Name of the institution: | State Shared Service Centre
Address: | Lõkke 4, 10122 Tallinn
Name of the contact person: | Janika Otsing
Position: | financial specialist
Email: | janika.otsing@rtk.ee
Phone number: | +3726631926
The Paying Authority hereby certifies
(i) to have checked the conformity of the Reimbursement Request with the financial stipulations, in particular the co-financing rate, set out in the relevant Support Measure Agreement; (ii) to have received sufficient information for the certification of the Reimbursement Request; (iii) to have checked the compliance of the Reimbursement Request with the information available to the Paying Authority; (iv) that the co-financing of the Partner State has been provided in accordance with the relevant Support Measure Agreement; (v) that based on the information available to the Paying Authority no double-financing could be identified; (vi) that recoverable VAT is not included in the Reimbursement Request as eligible expense.
The bank details for reimbursement are as follows:
Beneficiary: Ministry of Finance of the Republic of Estonia
IBAN: EE891010220034796011
SWIFT: EEUHEE2X
Reference: 2550081357
Name: Karin Viikmaa | Position: | Head of the Grants Payment Department
Date and signature | digitally signed
Note on A4: - Please fill out first the green fields in this sheet "Reimbursement Request" and only afterwards continue with the "Financial Progress" sheet and the other sheets - Indicate the number of the Reimbursement Request to get the data from the respective Reporting Period in the "Financial Progress" Sheet - In case of the last reimbursement request to be submitted to Switzerland, change the title to "Final Reimbursement Request" - Please note the comments with further instructions indicated by the red triangle in the cells - The sheet is protected without a password, to avoid unintentional deletion of a formula. You can press "unprotect sheet" to edit protected cells. - When submitting the Reimbursement Request to Switzerland, please send the signed version (e.g. PDF) as well as the Excel file. This sheet contains formulas to facilitate the preparation of the Reimbursement Request. It remains the responsibility of the Paying Authority to verify the correct calculations
Note on A10: please enter start and end date in the sheet "Financial Progress" in the respective column of the Reporting Period
Note on A11: Select a number between 1-14. According to your selection, the data from respective columns in the sheet "financial progress" Reporting Period will be gathered.
Note on A13: Please insert the amount as fixed in the Support Measure Agreement (Art 3 in SMA Template)
Note on A15: 1 CHF = amount in local currency This is the exchange rate from the sheet "Financial Progress" from the selected Reimbursement Request Number. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on B18: Value from sheet "Financial Progress". Ensure that the correct Reimbursement Request No is selected above.
Note on A20: The deducted amount of the financial correction in CHF should be calculated using the exchange rate applicable to the relevant Reimbursement Request to which the correction is linked. If the amount related to the irregularity was not included in any Reimbursement Request, the relevant exchange rate used in the Irregularity Report (immediate or regular) should be used. The total amount of deductions shall be entered here manually and further explained in the sheet "financial progress" "Information on deductions related to financial corrections (Art 11.4/3 Regulations)"
Note on A31: As the institutional set-up is country-specific, each partner state may adapt the certifications as appropriate in their specific institutional context and in line with the Regulations (namely Article 8.2).

## Financial Progress
Swiss-Estonian Cooperation Programme
Bio-Diversity Programme / Reimbursement Request No. 1
Financial Progress
Instructions
[5 empty] | 1a | 1b | 1c | 1d | 2a | 2b | 2c | 2d | 3a | 3b | 3c | 3d | 4a | 4b | 4c | 4d | 5a | 5b | 5c | 5d | 6a | 6b | 6c | 6d | 7a | 7b | 7c | 7d | 8a | 8b | 8c | 8d | 9a | 9b | 9c | 9d | 10a | 10b | 10c | 10d | 11a | 11b | 11c | 11d | 12a | 12b | 12c | 12d | 13a | 13b | 13c | 13d | 14a | 14b | 14c | 14d
BUDGET |  |  |  |  | REPORTING PERIOD 1: |  | 2024-05-01 | 2025-06-30 | REPORTING PERIOD 2: |  | start date | end date | REPORTING PERIOD 3: |  | start date | end date | REPORTING PERIOD 4: |  | start date | end date | REPORTING PERIOD 5: |  | start date | end date | REPORTING PERIOD 6: |  | start date | end date | REPORTING PERIOD 7: |  | start date | end date | REPORTING PERIOD 8: |  | start date | end date | REPORTING PERIOD 9: |  | start date | end date | REPORTING PERIOD 10: |  | start date | end date | REPORTING PERIOD 11: |  | start date | end date | REPORTING PERIOD 12: |  | start date | end date | REPORTING PERIOD 13: |  | start date | end date | REPORTING PERIOD 14: |  | start date | end date | CUMULATIVE DATA | [6 empty] | PLANNING
|  | EUR | % | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR |  |  | CHF |  |  |  | CHF | CHF | CHF
No | Budget items | Budget 100% | Co-financing rate (CH co-financing) | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | % of Budget spent | Total remaining Budget | Eligible Expenditures 100% | Swiss contribution (co-financing) | % of Swiss Contribution spent | Total remaining Swiss contribution | Reimbursements expected to be received from Switzerland (current year) | Reimbursements expected to be received from Switzerland (year +1) | Reimbursements expected to be received from Switzerland (year +2)
| Exchange rate CHF/EUR | 1.0361 |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 2 |  |  |  | 1
1 | Management Costs | 247384 | 85% | 202953.63 | 34210.56 | 34210.56 | 5131.58 | 29078.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34210.56 | 13.83% | 213173.44 | 34210.56 | 29078.98 | 14.33% | 173874.65 | 0 | 52000 | 52000
1.1 | Personnel | 71760 |  |  | 11986.39 | [55 empty] | 11986.39 | 16.7% | 59773.61
1.2 | Expenses of State Shared Service Centre for verification of incurred expenditure | 72800 |  |  | 3895.71 | [55 empty] | 3895.71 | 5.351% | 68904.29
1.3 | Swiss experts and partners | 0 |  |  | 0 | [55 empty] | 0 | #DIV/0! | 0
1.3 | Information and communication | 57420 |  |  | 14881.88 | [55 empty] | 14881.88 | 25.92% | 42538.12
1.4 | Miscellaneous | 45404 |  |  | 3446.58 | [55 empty] | 3446.58 | 7.591% | 41957.42
1.6 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
2 | Programme Component 1 "Development of innovative monitoring technolo-gies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency) | 3514862 | 85% | 2883589.89 | 189976.42 | 189976.42 | 28496.46 | 161479.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189976.42 | 5.405% | 3324885.58 | 189976.42 | 161479.96 | 5.6% | 2722109.93 | 0 | 1236500 | 807600
2.1 | Management costs Programme Component 1 | 301700 | . |  | 56991.21 | [55 empty] | 56991.21 | 18.89% | 244708.79
2.2 | Swiss experts and partners | 0 |  |  | 0 | [55 empty] | 0 | #DIV/0! | 0
2.2 | Activity 1: Development of new monitoring methods | 1927562 |  |  | 88406.86 | [55 empty] | 88406.86 | 4.586% | 1839155.14
2.3 | Activity 2: Development of IT systems | 1285600 |  |  | 44578.35 | [55 empty] | 44578.35 | 3.468% | 1241021.65
2.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
3 | Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board) | 4684861 | 85% | 3843456.11 | 445675.53 | 445675.53 | 66851.33 | 378824.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445675.53 | 9.513% | 4239185.47 | 445675.53 | 378824.2 | 9.856% | 3464631.91 | 0 | 1215000 | 1310000
3.1 | Management costs Programme Component 2 | 961111.14 |  |  | 77679.89 | [55 empty] | 77679.89 | 8.082% | 883431.25
3.2 | Swiss experts and partners | 0 |  |  | 0 | [55 empty] | 0 | #DIV/0! | 0
3.2 | Activity 1: Conservation Management Effectiveness Assessment | 492515.41 |  |  | 37933.81 | [55 empty] | 37933.81 | 7.702% | 454581.6
3.3 | Activity 2: Conservation Management Planning | 1916120.91 |  |  | 216266.56 | [55 empty] | 216266.56 | 11.29% | 1699854.35
3.4 | Activity 3: Species Protection | 1315113.54 |  |  | 113795.27 | [55 empty] | 113795.27 | 8.653% | 1201318.27
4 | Programme Component 3 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
4.1 | Management costs Programme Component 3 | [59 empty] | 0 | #DIV/0! | 0
4.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
4.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
4.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
4.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
5 | Programme Component 4 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
5.1 | Management costs Programme Component 4 | [59 empty] | 0 | #DIV/0! | 0
5.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
5.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
5.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
5.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
6 | Programme Component 5 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
6.1 | Management costs Programme Component 5 | [59 empty] | 0 | #DIV/0! | 0
6.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
6.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
6.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
6.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
7 | Programme Component 6 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
7.1 | Management costs Programme Component 3 | [59 empty] | 0 | #DIV/0! | 0
7.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
7.3 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
7.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
7.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
8 | Programme Component 7 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
8.1 | Management costs Programme Component 7 | [59 empty] | 0 | #DIV/0! | 0
8.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
8.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
8.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
8.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
9 | Programme Component 8 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
9.1 | Management costs Programme Component 8 | [59 empty] | 0 | #DIV/0! | 0
9.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
9.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
9.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
9.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
10 | Programme Component 9 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
10.1 | Management costs Programme Component 9 | [59 empty] | 0 | #DIV/0! | 0
10.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
10.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
10.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
10.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
| TOTAL | 8447107 | 85% | 6929999.63 | 669862.51 | 669862.51 | 100479.37 | 569383.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669862.51 | 7.93% | 7777244.49 | 669862.51 | 569383.14 | 8.216% | 6360616.49 | 0 | 2503500 | 2169600
Information on modifications of the Support Measure approved during the reporting period According to Regulation Article 4.12
No modifications of the Support Measure were approved during the reporting period.
Information on non-eligible expenditures during the reporting period Please indicate the amount of non-eligible expenditures during the reporting period. Why are the expenditures non-eligible (for example due to irregularities or because it was agreed during the approval process of the SM that the costs are non-eligible)? Who will finance the non-eligible expenditures?
No non-eligible expenditures were found.
Information on deductions related to financial corrections (Art 11.4/3 Regulations) In case of a financial correction already paid by Switzerland and deducted in this Reimbusement Request, please indicate the budget item, reporting period in question and provide explanation on the deduction made / refer to irregularity report.
There were no deductions.
Information on advance payments According to Art. 8.3. of the Regulations the Partner State may in exceptional cases agree with Switzerland on advance payments. If these are foreseen in the Support Measure Agreement, describe how the advance payment will be used in the upcoming reimbursement period and provide proof for the execution of the advance payment by the Partner State.
Advance payments were not foreseen.
Information regarding deviations from financial planning If there is a significant difference between the expenditures planned for this reporting period and the actual expenditures paid by the Paying Authority, justify the deviations. Also explain if the financial planning in this reimbursement request significantly differs from the financial planning in the previous reimbursement requests.If there is a cost overrun per budget item, describe how the additional costs will be covered.
Programme Component 2 reimbursment request is lower than planned because the central procurements of the institution took longer and the signing of the contracts was delayed.
Note on A4: - Please fill out first the green fields in this sheet "Reimbursement Request" and only afterwards continue with the "Financial Progress" sheet and the other sheets - Up to 14 Reimbursement Requests reporting periods are integrated in this sheet. Select the No in the "Reimbursement Request" sheet and use hide/unhide function to show the needed columns. - Dark grey cells can be left empty, green cells can be filled out. - Please note the comments with further instructions indicated by the red triangle in the cells - The sheet is protected without a password, to avoid unintentional deletion of a formula. This sheet contains formulas to facilitate the preparation of the Reimbursement Request. It remains the responsibility of the Paying Authority to verify the correct calculations.
Note on H6: insert start date of reporting period
Note on I6: insert end date of reporting period
Note on L6: insert start date of reporting period
Note on M6: insert end date of reporting period
Note on P6: insert start date of reporting period
Note on Q6: insert end date of reporting period
Note on T6: insert start date of reporting period
Note on U6: insert end date of reporting period
Note on X6: insert start date of reporting period
Note on Y6: insert end date of reporting period
Note on AB6: insert start date of reporting period
Note on AC6: insert end date of reporting period
Note on AF6: insert start date of reporting period
Note on AG6: insert end date of reporting period
Note on AJ6: insert start date of reporting period
Note on AK6: insert end date of reporting period
Note on AN6: insert start date of reporting period
Note on AO6: insert end date of reporting period
Note on AR6: insert start date of reporting period
Note on AS6: insert end date of reporting period
Note on AV6: insert start date of reporting period
Note on AW6: insert end date of reporting period
Note on AZ6: insert start date of reporting period
Note on BA6: insert end date of reporting period
Note on BD6: insert start date of reporting period
Note on BE6: insert end date of reporting period
Note on BH6: insert start date of reporting period
Note on BI6: insert end date of reporting period
Note on A8: Budget No should follow the same logic as indicated in the template, i.e. integer Numbers = main budget headings 1.1, 1.2, 1.3 etc = budget items Please use the same logic when adding additional budget headings / items
Note on B8: Budget items should be listed according to the budget in the Support Measure Agreement. If the budget in the Support Measure Agreement is amended, the budget in all Reimbursement Requests following the amendment shall be adapted accordingly. In case of Programmes, each Programme Component must be a separate budget heading item. The first budget heading is always the Programme Management. In case of the Support Measure Preparation Fund, preparation funds for each Support Measure should be listed as a separate budget item. In case of the Technical Assistance Fund, budget items to be structured according to the eligible tasks described in Art. 6.5 of the Regulations.
Note on BQ8: Please enter the amount that Switzerland is expected to contribute in the current and the next two calendar years. Please note that the Swiss reimbursements are always postponed by half a year compared to the payments. For the following year, for example, you must enter what Switzerland is expected to reimburse for the expenditures for the second half of the current year and the first semester of the following year.
Note on C9: 1 CHF = amount in local currency Please indicate the exchange rate as defined in the Budget of the Support Measure Agreement
Note on F9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on J9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on N9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on R9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on V9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on Z9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AD9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AH9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AL9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AP9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AT9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AX9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on BB9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on BF9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on D10: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D17: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D23: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D29: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D35: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D41: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D47: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D53: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D59: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D65: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.

## Operational Progress
Swiss-Estonian Cooperation Programme
Bio-Diversity Programme / Reimbursement Request No. 1
Operational Progress
Management Costs
No | Short description of activities undertaken in the reporting period
1.1 | Personnel Preparation of different legal documents, annual reports etc. - Government Regulation „The conditions and procedures for the use of funding under the Swiss-Estonian Cooperation Programme“ was approved in July 2024 and came into force on 6 August 2024. - The first Steering Committee meeting was held in October 2024. The Steering Committee agreed on the rules of procedure, and the Programme Operator and Programme Component Operators provided an overview of the developments within the „Biodiversity Programme“. - Support measure implementation agreement between the NCU and the Programme Operator was signed on December 19, 2024. - The Minister´s directive for the implementation of programme components was signed on 28th of February 2025. - The Annual Support Measure Report was submitted to the NCU on 30 March 2025, including a revised implementation schedule and procurement plan. - Second Steering Committee meeting and a monitoring mission were organised in Saaremaa. - Submission of the Reimbursement Request is planned for September 2025. - The third Steering Committee meeting is tentatively scheduled for September or October 2025.
1.2 | Expenses of State Shared Service Centre for verification of incurred expenditure The NCU verified the expenditures of the support measure.
1.3 | Information and communication The Ministry of Climate organized the opening event on 30 May 2024 at Palmse manor. Event was successful, with approximately 75 participants. Also the press release and social media post were published.
1.4 | Miscellaneous Study trip and monitoring mission. The Programme Operator participated in a study trip to Switzerland with Programme Component 1 to learn about bird radars. The Programme Operator organised the second Steering Committee meeting and a monitoring mission in Saaremaa on 15–16 April 2025.
Estimated cumulative physical progress (%)
Programme Component 1 "Development of innovative monitoring technolo-gies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency)
No | Short description of activities undertaken in the reporting period
2.1 | Management of the programme component 2024 was preparatory period for the component. Personnel was recruited: project manager, monitoring specialist, monitoring assistant, IT-system specialist, IT project manager and data manager were contracted for the whole period of the programme component operation. Monitoring assistant was already re-contracted during the period, as the work appeared to be more effective when there will be two persons working on 0,5 FTE instead of one full time. Activities were launched: Development of new monitoring methods started with many meetings between project team and monitoring team of Estonian Environment Agency in order to plan methodologies as well as technology purchase. Preparatory work contained preparation of documents for different purchases and procurements as well as two study trips that were held: for getting deeper knowledre of wolf monitoring methods as well as obtain better knowledge base on monitoring of bird migration with radars. Testing of REM model monitoring was also launched in very first days of the programme component operation. Also development of IT systems had preparatory phase and all three team members worked together with state level specialists on preparation for purchasing development in next years. Together with Environmental Board and Ministry of Climate many meetings were held on IT-developments planning.
2.2 | Activity 1. Development of new monitoring methods Random Encounter Method (REM) has been under practical testing and software development in order to involve AI has been also under testing phase during the 2024. Testing of REM during the spring period of 2024 was done in 39 monitoring areas. For acquisition of mobile 3D bird radars study trip was organised in 27th to 29th of October 2024 to Zurich, Swizerland into the factory of one of the swiss radar producer: Swiss Birdradar Solution AG. For acquisition and testing of new technologies for wildlife biodiversity monitoring first purchase was prepared by the end of the year and following devices were received: rugged tablets; bat-detectors attachable to mobile phones; bird sound recorders with GPS attached; GPS-devices compatible with existing bird sound recorders; drone with thermal camera; binoculars with distance meter and altimeter; binoculars with thermal camera; fully automated insect monitoring devices. One very important study trip was held in 16th of September to 2nd of October in 2024: wolf expert of Estonia got very valuable information and hands on experiences on wolf monitoring in USA (Idaho, Montana and Washington States). Testing of eDNA usage in biodiversity monitoring methods has been divided into two parts: first testing set has been started during the second half of 2024 and it includes testing eDNA usability and method cost-effectiveness in aquatic environment (rivers) with focus on species identification (crayfish, mussels, dragon-flies, diving beetles) and distribution detection (Habitat directive Fish species). In promoting citizen science and creating network of volunteers 2024 has been preparatory and planning period. Four voluntary monitoring methods, for monitoring otter, diving beetles, bats and amphibians were tested during 2024.
2.3 | Activity 2. Development of IT systems For a development of IT systems (establishment of interfaces between KESE and EELIS; establishment of interface between EELIS and eBiodiversity (PlutoF); development of management plans assessment tool and development of fieldwork tool) 2024 was a preparatory phase: framework contract was signed in September 2024 between IT Centre of the Ministry of the Environment and IT developer (Inversion Software OÜ) that won the framework procurement for IT developments in IT-plan of Ministry of Climate for next four years (2025-2028). Preparation of cooperation contract between Estonian Environment Agency and IT Centre of the Ministry of the Environment in order to set up framework for all four developments listed above. EELIS2 (new version of IT-system) has been under testing by Chief Specialist (IT system specialist) in the Environmental Agency (responsible for the input of the IT developments and testing). That specialist also participated in weekly EELIS2 development meetings and EELIS1 (old IT-system) development meetings as well as workshops for different feedback to developer (massive data import, data handling, protected areas and objects, data forms, object migration etc). Specialist (data manager) in the Environmental Agency has been manually transporting data from KESE to EELIS, testing same time details for interface development, also testing Tableau analytics and open data. All four developments/interfaces will be performed during next periods of the programme.
Estimated cumulative physical progress (%)
Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board)
No | Short description of activities undertaken in the reporting period
3.1 | Management of the programme component The project team has been put together(specialists and experts hired) and activities have started. The exact plan of inventories, expert opinions, management plans, action plans etc has been discussed and prepared, general principles discussed. The preparation for national procurements has been carried out. Communication activities, a study trip and seminars have been organised.
3.2 | Activity 1: Conservation Management Effectiveness Assessment. 2024 was the preparatory phase for the management effectiveness assessment: procedures of the assessment within the Environmental Board were put together, roles of different departments were described, discussions were carried out. The coordinator put together the list of areas that will be assessed in 2025 (109 sites) and cooperated with the Environmental Agency and the Forest Management Centre about how to gather data necessary for the assessment, initial discussions about the assessment IT tool have taken place. In 2024 the coordinator was hired, foru assessors were hired from January 1, 2025. Each member assesses 3 sites per month, by April approximately 30 sites were assessed.
3.3 | Activity 2: Conservation Management Planning The guidelines for management plans have been updated and include all the compulsory (legally required) topics. The testing of the changes of the guidelines was carried out. A data sheet was put together about protected areas using the data analytics tool Tableau and the information will be provided on the web page in the environmental portal (keskkonnaportaal.ee). The project team put together the list of pressures and threats that can be used for Estonian habitats and species and chose the possible pressures and threats for each habitat. The same was done with measures. Project experts have started putting together action plans for habitats. The compilation of two action plans has been started: rivers and streams, lakes. The new guidelines for inventories of lakes has been put together. A web map for inventories has been put together and made public. By mid-April 35 contracts were signed for carrying out inventories and compiling expert opinions and 11 management plans were under preparation. In 2024 two coordinators, two experts of habitat action plans and five management plan specialists were hired. Also, for all the activities, one data specialist and one analyst were hired.
3.4 | Activity 3: Species Protection Updating the guidelines of species’ action plans has been carried out. The same principles as there were in the guidelines of management plans have been used: there is a new system of pressures, threats and protection measures used. The new topics are included, e.g. when to archive/delete the species’ habitats. All the data of previous action plans and draft copies was gathered, discussions about what species need action plans and how to make the process of putting together action plans easier were carried out with the Ministry of Climate. Species were grouped and it was decided that some species’ groups can have a joint action plan, other species can have short action plans. Action plans are being compiled. in 2024 four contracts for inventories were signed and by mid-April 30 technical proposals were sent for tender. Changing the categories of protected species: data on all the protected species has been collected and analysed, principles of assessing the categories of species have been put together and discussed with the Ministry of Climate. On January 22, 2025 the kick-off seminar was organised by the project team, Estonian best species experts were invited to the seminar. 119 people participated in Tartu and more than 140 people listened to the seminar online. In the first half of 2025 expert groups of 8 species groups have had discussions. In 2024 a coordinator, an expert and one action plan specialist were hired.
Estimated cumulative physical progress (%)
Note on A7: Please insert additional activities as needed; relate operational progress to the financial progress
Note on A15: Please insert additional activities as needed; relate physical progress to the financial progress
Note on A22: Please insert additional activities as needed; relate physical progress to the financial progress

## Programme Characteristics
Swiss-Estonian Cooperation Programme
Bio-Diversity Programme / Reimbursement Request No. 1
Programme Characteristics
To be filled in by Programme Operator | [9 empty] | To be filled in by Switzerland (see SAP characteristics) | [6 empty] | To be filled in by Switzerland (see SAP characteristics)
No | Programme Component Name | Swiss Contribution CHF | Specific Objective | Thematic Area | (in-country) Geographic Focus | Name Programme Component Operator | Type of entity | Planned duration |  | Sector 1 | Sector 2 (SDC only) | Sector 3 (SDC only) | PM Support RIO CC Adaptations | PM Support RIO CC mitigation | PM Support RIO CC desertification | PM Support Social Inlcusion | PM Gender | PM Governance | PM Disabilities | PM Digitalisation | PM Support RIO biodiversity
PSP/PA | maximum 40 characters | in CHF | according to Art. 2.2 Regulations | according to Art. 2.4 Regulations |  |  |  | Start | End | use title, not code | use title, not code | use title, not code
1 | Management Costs | 202953.63 | Environment and climate | Biodiversity | national coverage | Ministry of Climate | National administration | 2024-05-01 | 2028-08-31
2 | Programme Component 1 "Development of innovative monitoring technolo-gies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency) | 2883589.89 | Environment and climate | Biodiversity | national coverage | Estonian Environment Agency | National administration | 2024-05-01 | 2028-04-30
3 | Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board) | 3843456.11 | Environment and climate | Biodiversity | national coverage | Environmental Board | National administration | 2024-05-01 | 2028-04-30
4 | Programme Component 3 | 0
5 | Programme Component 4 | 0
6 | Programme Component 5 | 0
7 | Programme Component 6 | 0
8 | Programme Component 7 | 0
9 | Programme Component 8 | 0
10 | Programme Component 9 | 0
delete or add lines as necessary
Note on A3: only to be completed and continuously updated for programmes
Note on A8: PSP / PA is internal number used in the CH Project management system.

## Procurement plan
Swiss-Estonian Cooperation Programme
Bio-Diversity Programme / Reimbursement Request No. 1
Procurement Plan
To be filled in by Programme Operator
Programme Component or Project Ref. No | Contract Name | If applicable, planned deadline for submitting documentation to Swiss "non objection" | Launch of tender planned | Tender notice will be submitted to Swiss side before publication | English translation of tender documents will be made available to bidders | Actual launch of tender (publication of tender notice) | Contract signature planned | Actual contract signature | Contract completion planned | Actual contract completion | Initially estimated costs |  | Actual costs based on signed contracts |  | Contractor | Expenditures incurred based on signed contracts |  | Comments
|  | quarter / year | quarter / year | yes/no | yes/no | date | quarter / year | date | quarter / year | date | EUR | CHF | EUR | CHF | name | EUR | CHF | status/ appeals/ cancelling or repetion of tender (incl. reason)/ numbers of bidders and rejected bids/risks/ irregularities related to the tender/ difficulties with the the Contractor/ suspension of works etc.
Programme Component 1 “Development of innovative monitoring technologies/solutions and improvement of Environmental databases and systems” | Purchasing mobile 3D bird radar | 2024 | 2024 | yes | yes | 19/05/2025 | 1Q/2025 |  | 4Q/2025 |  | 990000 | 955524 | 675400 | 651879.535 | Swiss Birdradar Solution AG |  |  | Costs wihtout VAT. The contract is pending signature.
<
Note on A7: Provide an overview over all the procurements related to the SM. In case of Programmes, structure the table according to Programme Components. Unless otherwise agreed with Switzerland, only procurments above the threshold of CHF 150 000 must be listed. Insert a number. For related tenders use the same number and distinguish them using additional letters. For example, in case of a building renovation, there will be related tenders such as the technical project of the renovation (1a),the supervision of the renovation works (1b) and the renovation works (1c). The table is to be gradually updated and completed on a half-yearly basis.

## E-billing information
Deckblatt Rechnung E-Billing / Coversheet Invoice E-Billing
Buchungsinformationen / Booking information
Referenz-Nummer / Reference Number
Projektnummer / Support Measure Identification Code | 7F-10768.01
Kreditorennummer / Creditor Number | 1000643543
Name des Kreditors / Creditor's name | Ministry of Finance of the Republic of Estonia
Strasse / Street | Suur-Ameerika 1
PLZ, Ort / Zip code and place | 10122 Tallinn
Währung / Currency: | CHF
Betrag / Reimbursement requested from Switzerland | 569383.14
Aufteilung nach Programmkomponente / Breakdown by programme component
Management cost | 29078.98
Programme Component 1 | 161479.96
Programme Component 2 | 378824.2
Zahladresse / Account details
Kontoinhaber / bank account holder (if different from creditor name) | Ministry of Finance of the Republic of Estonia
IBAN-Nr.: | EE891010220034796011
SWIFT: | EEUHEE2X
Reference: | 2550081357
Bankbezeichnung / Name and address of the bank | SEB, Tornimäe 2, 15010 Tallinn, Estonia
Note on C5: The Reference Number, the Support Measure Identification Code and the Creditor Number are necessary for the e-billing in Switzerland. They will be provided by the Swiss side and remain the same throughout the implementation period.