## Procurement plan
#REF!
#REF!
Procurement Plan
To be filled in by Programme Operator
Programme Component or Project Ref. No | Contract Name | If applicable, planned deadline for submitting documentation to Swiss "non objection" | Launch of tender planned | Tender notice will be submitted to Swiss side before publication | English translation of tender documents will be made available to bidders | Actual launch of tender (publication of tender notice) | Contract signature planned | Actual contract signature | Contract completion planned | Actual contract completion | Initially estimated costs |  | Actual costs based on signed contracts |  | Contractor | Expenditures incurred based on signed contracts |  | Comments
|  | quarter / year | quarter / year | yes/no | yes/no | date | quarter / year | date | quarter / year | date | EUR | CHF | EUR | CHF | name | EUR | CHF | status/ appeals/ cancelling or repetion of tender (incl. reason)/ numbers of bidders and rejected bids/risks/ irregularities related to the tender/ difficulties with the the Contractor/ suspension of works etc.
Programme Management | Procurements above 150 000 CHF are not foreseen
Programme Component 1 “Development of innovative monitoring technologies/solutions and improvement of Environmental databases and systems”
| Purchasing mobile 3D bird radar | 2024 | 2024 | yes | yes |  | 1Q/2025 |  | 4Q/2025 | EUR: 990000; CHF: 955524
| Development of necessary connections between IT systems and field work tool | 2024 | 2025 | no | no |  | 4Q/2024 |  | 4Q/2025 | EUR: 300000; CHF: 289553 | Development of the necessary connections for the exchange of data between PlutoF and EELIS as well as KESE and EELIS; development of the fieldwork tool
| Development of management efficiency assesment tool, web forms and analytics | 2025 | 2026 | no | no |  | 1Q/2026 |  | 4Q/2027 | EUR: 400000; CHF: 386070 | Development of management efficiency assesment tool in EELIS and other necessary developments as web forms for Nature Observation Application, analytical solutions etc
| Development of new monitoring methods (eDNA) | 2024 | 2024 | no | no |  | 4Q/2024 |  | 4Q/2026 | EUR: 150000; CHF: 144776 | The requirements for the international procurement will be clarified during the market research.
Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” | Procurements above 150 000 CHF are not foreseen
<
Note on A7: Provide an overview over all the procurements related to the SM. In case of Programmes, structure the table according to Programme Components. Unless otherwise agreed with Switzerland, only procurments above the threshold of CHF 150 000 must be listed. Insert a number. For related tenders use the same number and distinguish them using additional letters. For example, in case of a building renovation, there will be related tenders such as the technical project of the renovation (1a),the supervision of the renovation works (1b) and the renovation works (1c). The table is to be gradually updated and completed on a half-yearly basis.