## Reimbursement Request
Swiss-Estonian Cooperation Programme
Reimbursement Request No. 2
Biodiversity Programme
Instructions |  |  |  |  | Estonia
A. Basic information
Support Measure Title | Biodiversity Programme
Support Measure Identification Code | Šveits.1.02 |  |  |  | 7F-10768.01
Support Measure duration | from | 2024-05-01 |  | to | 2028-08-31
Name of Executing Agency (EA)
Reporting period | from | 2025-07-01 |  | to | 2025-12-31
Reimbursement Request No | 2
Total Support Measure Budget (local currency) | 8447107 |  |  | EUR
Maximum Swiss contribution (CHF) | 6930000 |  | CHF
Swiss co-financing rate | on total budget |  | 85% | on total expenditures |  | 85%
Exchange rate used | CHF/EUR | 1 |  | Date of exchange rate |  | 2025-09-15
B. Amount requested by the Paying Authority
Total amount requested | 580963.59 |  |  | EUR | 580963.59 | CHF
National co-financing | 87144.54 |  |  | EUR | 87144.54 | CHF
Deductions (according to Regulations 11.4/3) | 0 |  |  | EUR | 0 | CHF
Swiss co-financing = Reimbursement by CH | 493819.05 |  |  | EUR | 493819.05 | CHF
C. Available amount from the Swiss Contribution
Maximum Swiss Contribution | 6930000 |  |  | CHF | 100%
Cumulative amount received from Switzerland | 532031.61 |  |  | CHF | 7.68%
Available amount before the current reimbursement | 6397968.39 |  |  | CHF | 92.32%
Total amount of current reimbursement request | 493819.05 |  |  | CHF | 7.13%
Remaining amount after the current reimbursement | 5904149.34 |  |  | CHF | 85.2%
D. Certification and approval of Reimbursement Request
Executing Agency: Programme Operator
Name of the institution: | Ministry of Climate
Address: | Suur-Ameerika 1, 10122 Tallinn, Estonia
Name of the contact person: | Kairi Toiger
Position: | Advisor, financial department
Email: | kairi.toiger@kliimaministeerium.ee
Phone number: | 3726262931
The Executing Agency hereby certifies
(i) that the Support Measure is implemented in accordance with the Support Measure Agreement and Support Measure Implementation Agreement; (ii) the reporting under Physical Progress, Financial Progress and Procurement Plan is true and accurate; (iii) that the reporting under Financial Progress reflects correctly the incurred expenditures; (iv) that recoverable VAT is not included in the Financial Progress as eligible expense; (v) that no double-financing occurs; (vi) that all procurements for which expenditures were incurred during the reporting period have been conducted in compliance with the applicable law of the Partner State and EU directives on public procurement.
Name: Marten Kokk | Position: | Secretary General
Place, date and signature | digitally signed
National Coordination Unit
Name of the institution: | State Shared Service Centre
Address: | Lõkke 4, 10122 Tallinn
Name of the contact person: | Helena Musthallik
Position: | programme expert
Email: | helena.musthallik@rtk.ee
Phone number: | +37256466003
The National Coordination Unit hereby certifies
(i) that the information and financial data provided in this Reimbursement Request has been thoroughly reviewed and found to be correct, reliable and accurate; (ii) that claimed expenditures are incurred as part of the Support Measure in accordance with the Framework Agreement, the relevant Support Measure Agreement and Support Measure Implementation Agreement; (iii) that all payments declared have actually been made in the indicated (or exceptionally previous) reporting period. (iv) the compliance with state aid rules of all activities performed in the reporting period.
Name: Urmo Merila | Position: | Deputy Director General
Date and signature | digitally signed
Paying Authority
Name of the institution: | State Shared Service Centre
Address: | Lõkke 4, 10122 Tallinn
Name of the contact person: | Janika Otsing
Position: | financial specialist
Email: | janika.otsing@rtk.ee
Phone number: | +3726631926
The Paying Authority hereby certifies
(i) to have checked the conformity of the Reimbursement Request with the financial stipulations, in particular the co-financing rate, set out in the relevant Support Measure Agreement; (ii) to have received sufficient information for the certification of the Reimbursement Request; (iii) to have checked the compliance of the Reimbursement Request with the information available to the Paying Authority; (iv) that the co-financing of the Partner State has been provided in accordance with the relevant Support Measure Agreement; (v) that based on the information available to the Paying Authority no double-financing could be identified; (vi) that recoverable VAT is not included in the Reimbursement Request as eligible expense.
The bank details for reimbursement are as follows:
Beneficiary: Ministry of Finance of the Republic of Estonia
IBAN: EE891010220034796011
SWIFT: EEUHEE2X
Reference: 2550081357
Name: Karin Viikmaa | Position: | Head of the Grants Payment Department
Date and signature | digitally signed
Note on A4: - Please fill out first the green fields in this sheet "Reimbursement Request" and only afterwards continue with the "Financial Progress" sheet and the other sheets - Indicate the number of the Reimbursement Request to get the data from the respective Reporting Period in the "Financial Progress" Sheet - In case of the last reimbursement request to be submitted to Switzerland, change the title to "Final Reimbursement Request" - Please note the comments with further instructions indicated by the red triangle in the cells - The sheet is protected without a password, to avoid unintentional deletion of a formula. You can press "unprotect sheet" to edit protected cells. - When submitting the Reimbursement Request to Switzerland, please send the signed version (e.g. PDF) as well as the Excel file. This sheet contains formulas to facilitate the preparation of the Reimbursement Request. It remains the responsibility of the Paying Authority to verify the correct calculations
Note on A10: please enter start and end date in the sheet "Financial Progress" in the respective column of the Reporting Period
Note on A11: Select a number between 1-14. According to your selection, the data from respective columns in the sheet "financial progress" Reporting Period will be gathered.
Note on A13: Please insert the amount as fixed in the Support Measure Agreement (Art 3 in SMA Template)
Note on A15: 1 CHF = amount in local currency This is the exchange rate from the sheet "Financial Progress" from the selected Reimbursement Request Number. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on B18: Value from sheet "Financial Progress". Ensure that the correct Reimbursement Request No is selected above.
Note on A20: The deducted amount of the financial correction in CHF should be calculated using the exchange rate applicable to the relevant Reimbursement Request to which the correction is linked. If the amount related to the irregularity was not included in any Reimbursement Request, the relevant exchange rate used in the Irregularity Report (immediate or regular) should be used. The total amount of deductions shall be entered here manually and further explained in the sheet "financial progress" "Information on deductions related to financial corrections (Art 11.4/3 Regulations)"
Note on A31: As the institutional set-up is country-specific, each partner state may adapt the certifications as appropriate in their specific institutional context and in line with the Regulations (namely Article 8.2).

## Financial Progress
Swiss-Estonian Cooperation Programme
Biodiversity Programme / Reimbursement Request No. 2
Financial Progress
Instructions
[5 empty] | 1a | 1b | 1c | 1d | 2a | 2b | 2c | 2d | 3a | 3b | 3c | 3d | 4a | 4b | 4c | 4d | 5a | 5b | 5c | 5d | 6a | 6b | 6c | 6d | 7a | 7b | 7c | 7d | 8a | 8b | 8c | 8d | 9a | 9b | 9c | 9d | 10a | 10b | 10c | 10d | 11a | 11b | 11c | 11d | 12a | 12b | 12c | 12d | 13a | 13b | 13c | 13d | 14a | 14b | 14c | 14d
BUDGET |  |  |  |  | REPORTING PERIOD 1: |  | 2024-05-01 | 2025-06-30 | REPORTING PERIOD 2: |  | 2025-07-01 | 2025-12-31 | REPORTING PERIOD 3: |  | start date | end date | REPORTING PERIOD 4: |  | start date | end date | REPORTING PERIOD 5: |  | start date | end date | REPORTING PERIOD 6: |  | start date | end date | REPORTING PERIOD 7: |  | start date | end date | REPORTING PERIOD 8: |  | start date | end date | REPORTING PERIOD 9: |  | start date | end date | REPORTING PERIOD 10: |  | start date | end date | REPORTING PERIOD 11: |  | start date | end date | REPORTING PERIOD 12: |  | start date | end date | REPORTING PERIOD 13: |  | start date | end date | REPORTING PERIOD 14: |  | start date | end date | CUMULATIVE DATA | [6 empty] | PLANNING
|  | EUR | % | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR |  |  | CHF |  |  |  | CHF | CHF | CHF
No | Budget items | Budget 100% | Co-financing rate (CH co-financing) | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | % of Budget spent | Total remaining Budget | Eligible Expenditures 100% | Swiss contribution (co-financing) | % of Swiss Contribution spent | Total remaining Swiss contribution | Reimbursements expected to be received from Switzerland (current year) | Reimbursements expected to be received from Switzerland (year +1) | Reimbursements expected to be received from Switzerland (year +2)
| Exchange rate CHF/EUR | 1.0361 |  |  | 1.0702 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 2 |  |  |  | 1
1 | Management Costs | 247384 | 85% | 202953.63 | 34210.56 | 31966.35 | 4794.95 | 27171.4 | 8522.81 | 8522.81 | 1278.42 | 7244.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42733.37 | 17.27% | 204650.63 | 40489.16 | 34415.79 | 16.96% | 168537.84 | 30000 | 52000 | 86537.84
1.1 | Personnel | 71760 |  |  | 11986.39 |  |  |  | 4712.44 | [51 empty] | 16698.83 | 23.27% | 55061.17
1.2 | Expenses of State Shared Service Centre for verification of incurred expenditure | 72800 |  |  | 3895.71 |  |  |  | 3307.48 | [51 empty] | 7203.19 | 9.894% | 65596.81
1.3 | Swiss experts and partners | 0 |  |  | 0 | [55 empty] | 0 | #DIV/0! | 0
1.3 | Information and communication | 57420 |  |  | 14881.88 |  |  |  | 450 | [51 empty] | 15331.88 | 26.7% | 42088.12
1.4 | Miscellaneous | 45404 |  |  | 3446.58 |  |  |  | 52.89 | [51 empty] | 3499.47 | 7.707% | 41904.53
1.6 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
2 | Programme Component 1 "Development of innovative monitoring technolo-gies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency) | 3514862 | 85% | 2883589.89 | 189976.42 | 177513.97 | 26627.1 | 150886.87 | 171790.78 | 171790.78 | 25768.62 | 146022.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361767.2 | 10.29% | 3153094.8 | 349304.75 | 296909.03 | 10.3% | 2586680.86 | 983280 | 929560 | 673840.86
2.1 | Management costs Programme Component 1 | 301700 | . |  | 56991.21 |  |  |  | 47631.08 | [51 empty] | 104622.29 | 34.68% | 197077.71
2.2 | Swiss experts and partners | 0 |  |  | 0 | [55 empty] | 0 | #DIV/0! | 0
2.2 | Activity 1: Development of new monitoring methods | 1927562 |  |  | 88406.86 |  |  |  | 91069.04 | [51 empty] | 179475.9 | 9.311% | 1748086.1
2.3 | Activity 2: Development of IT systems | 1285600 |  |  | 44578.35 |  |  |  | 33090.66 | [51 empty] | 77669.01 | 6.041% | 1207930.99
2.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
3 | Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board) | 4684861 | 85% | 3843456.11 | 445675.53 | 416439.22 | 62465.88 | 353973.34 | 400650 | 400650 | 60097.5 | 340552.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846325.53 | 18.07% | 3838535.47 | 817089.22 | 694525.84 | 18.07% | 3148930.27 | 950000 | 1215000 | 983930.27
3.1 | Management costs Programme Component 2 | 961111.14 |  |  | 77679.89 |  |  |  | 74212 | [51 empty] | 151891.89 | 15.8% | 809219.25
3.2 | Swiss experts and partners | 0 |  |  | 0 | [55 empty] | 0 | #DIV/0! | 0
3.2 | Activity 1: Conservation Management Effectiveness Assessment | 492515.41 |  |  | 37933.81 |  |  |  | 67889.81 | [51 empty] | 105823.62 | 21.49% | 386691.79
3.3 | Activity 2: Conservation Management Planning | 1916120.91 |  |  | 216266.56 |  |  |  | 156284.53 | [51 empty] | 372551.09 | 19.44% | 1543569.82
3.4 | Activity 3: Species Protection | 1315113.54 |  |  | 113795.27 |  |  |  | 102263.66 | [51 empty] | 216058.93 | 16.43% | 1099054.61
4 | Programme Component 3 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
4.1 | Management costs Programme Component 3 | [59 empty] | 0 | #DIV/0! | 0
4.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
4.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
4.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
4.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
5 | Programme Component 4 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
5.1 | Management costs Programme Component 4 | [59 empty] | 0 | #DIV/0! | 0
5.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
5.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
5.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
5.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
6 | Programme Component 5 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
6.1 | Management costs Programme Component 5 | [59 empty] | 0 | #DIV/0! | 0
6.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
6.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
6.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
6.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
7 | Programme Component 6 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
7.1 | Management costs Programme Component 3 | [59 empty] | 0 | #DIV/0! | 0
7.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
7.3 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
7.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
7.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
8 | Programme Component 7 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
8.1 | Management costs Programme Component 7 | [59 empty] | 0 | #DIV/0! | 0
8.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
8.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
8.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
8.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
9 | Programme Component 8 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
9.1 | Management costs Programme Component 8 | [59 empty] | 0 | #DIV/0! | 0
9.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
9.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
9.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
9.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
10 | Programme Component 9 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
10.1 | Management costs Programme Component 9 | [59 empty] | 0 | #DIV/0! | 0
10.2 | Swiss experts and partners | [59 empty] | 0 | #DIV/0! | 0
10.3 | Activity XY | [59 empty] | 0 | #DIV/0! | 0
10.4 | Activity YZ | [59 empty] | 0 | #DIV/0! | 0
10.5 | add lines as needed | [59 empty] | 0 | #DIV/0! | 0
| TOTAL | 8447107 | 85% | 6929999.63 | 669862.51 | 625919.54 | 93887.93 | 532031.61 | 580963.59 | 580963.59 | 87144.54 | 493819.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250826.1 | 14.81% | 7196280.9 | 1206883.13 | 1025850.66 | 14.8% | 5904148.97 | 1963280 | 2196560 | 1744308.97
Information on modifications of the Support Measure approved during the reporting period According to Regulation Article 4.12
No modifications of the Support Measure were approved during the reporting period.
Information on non-eligible expenditures during the reporting period Please indicate the amount of non-eligible expenditures during the reporting period. Why are the expenditures non-eligible (for example due to irregularities or because it was agreed during the approval process of the SM that the costs are non-eligible)? Who will finance the non-eligible expenditures?
No non-eligible expenditures were found.
Information on deductions related to financial corrections (Art 11.4/3 Regulations) In case of a financial correction already paid by Switzerland and deducted in this Reimbusement Request, please indicate the budget item, reporting period in question and provide explanation on the deduction made / refer to irregularity report.
There were no deductions.
Information on advance payments According to Art. 8.3. of the Regulations the Partner State may in exceptional cases agree with Switzerland on advance payments. If these are foreseen in the Support Measure Agreement, describe how the advance payment will be used in the upcoming reimbursement period and provide proof for the execution of the advance payment by the Partner State.
Advance payments were not foreseen.
Information regarding deviations from financial planning If there is a significant difference between the expenditures planned for this reporting period and the actual expenditures paid by the Paying Authority, justify the deviations. Also explain if the financial planning in this reimbursement request significantly differs from the financial planning in the previous reimbursement requests.If there is a cost overrun per budget item, describe how the additional costs will be covered.
Programme Component 2 reimbursment request is lower than planned because the central procurements of the institution took longer and the signing of the contracts was delayed.
Note on A4: - Please fill out first the green fields in this sheet "Reimbursement Request" and only afterwards continue with the "Financial Progress" sheet and the other sheets - Up to 14 Reimbursement Requests reporting periods are integrated in this sheet. Select the No in the "Reimbursement Request" sheet and use hide/unhide function to show the needed columns. - Dark grey cells can be left empty, green cells can be filled out. - Please note the comments with further instructions indicated by the red triangle in the cells - The sheet is protected without a password, to avoid unintentional deletion of a formula. This sheet contains formulas to facilitate the preparation of the Reimbursement Request. It remains the responsibility of the Paying Authority to verify the correct calculations.
Note on H6: insert start date of reporting period
Note on I6: insert end date of reporting period
Note on L6: insert start date of reporting period
Note on M6: insert end date of reporting period
Note on P6: insert start date of reporting period
Note on Q6: insert end date of reporting period
Note on T6: insert start date of reporting period
Note on U6: insert end date of reporting period
Note on X6: insert start date of reporting period
Note on Y6: insert end date of reporting period
Note on AB6: insert start date of reporting period
Note on AC6: insert end date of reporting period
Note on AF6: insert start date of reporting period
Note on AG6: insert end date of reporting period
Note on AJ6: insert start date of reporting period
Note on AK6: insert end date of reporting period
Note on AN6: insert start date of reporting period
Note on AO6: insert end date of reporting period
Note on AR6: insert start date of reporting period
Note on AS6: insert end date of reporting period
Note on AV6: insert start date of reporting period
Note on AW6: insert end date of reporting period
Note on AZ6: insert start date of reporting period
Note on BA6: insert end date of reporting period
Note on BD6: insert start date of reporting period
Note on BE6: insert end date of reporting period
Note on BH6: insert start date of reporting period
Note on BI6: insert end date of reporting period
Note on A8: Budget No should follow the same logic as indicated in the template, i.e. integer Numbers = main budget headings 1.1, 1.2, 1.3 etc = budget items Please use the same logic when adding additional budget headings / items
Note on B8: Budget items should be listed according to the budget in the Support Measure Agreement. If the budget in the Support Measure Agreement is amended, the budget in all Reimbursement Requests following the amendment shall be adapted accordingly. In case of Programmes, each Programme Component must be a separate budget heading item. The first budget heading is always the Programme Management. In case of the Support Measure Preparation Fund, preparation funds for each Support Measure should be listed as a separate budget item. In case of the Technical Assistance Fund, budget items to be structured according to the eligible tasks described in Art. 6.5 of the Regulations.
Note on BQ8: Please enter the amount that Switzerland is expected to contribute in the current and the next two calendar years. Please note that the Swiss reimbursements are always postponed by half a year compared to the payments. For the following year, for example, you must enter what Switzerland is expected to reimburse for the expenditures for the second half of the current year and the first semester of the following year.
Note on C9: 1 CHF = amount in local currency Please indicate the exchange rate as defined in the Budget of the Support Measure Agreement
Note on F9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on J9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on N9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on R9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on V9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on Z9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AD9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AH9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AL9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AP9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AT9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AX9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on BB9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on BF9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on D10: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D17: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D23: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D29: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D35: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D41: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D47: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D53: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D59: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D65: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.

## Operational Progress
Swiss-Estonian Cooperation Programme
Biodiversity Programme / Reimbursement Request No. 2
Operational Progress
Management Costs
No | Short description of activities undertaken in the reporting period
1.1 | Personnel Preparation of different legal documents, annual reports etc. - Reporting expenses in a domestic program - Preparation and submission of the Reimbursement Request. RR was submitted in September 2025. - Organising the third Steering Committee meeting in Ida-Virumaa on 6-7th October 2025.
1.2 | Expenses of State Shared Service Centre for verification of incurred expenditure The NCU verified the expenditures of the support measure.
1.3 | Information and communication Programme operator organised task force meetings. This budget line includes some costs related to a monitoring visit in Saaremaa in April 2025.
1.4 | Miscellaneous Study trip and monitoring visit. The Programme Operator participated in a study trip to Switzerland with Programme Component 2 to learn about national park. The Programme Operator organised the third Steering Committee meeting and a monitoring visit in Ida-Virumaa 6–7 October 2025.
Estimated cumulative physical progress (%)
Programme Component 1 "Development of innovative monitoring technolo-gies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency)
No | Short description of activities undertaken in the reporting period
2.1 | Management of the programme component Personnel managed. Procurement of 4 bird-radars and other innovative monitoring devices were managed and contracted. Preparation of integrating innovative devices into national biodiversity monitoring is launched in cooperation with monitoring team in Estonian Environment Agency. eDNA method testing contract was finalised and report handed over, acceptance will be expected in January 2026. 10 voluntary monitoring campaigns were finalised and next 10 prepared for 2026 together with substancial communication plan, including two big events as feedback for voluntary monitorers in 2026. Project IT development plan was promoted and needed institutions as well as contact persons networked. Cooperation contract with the IT Centre of the Ministry of the Environment (KEMIT) is in force and expenditures as well as developments plan is obtained.
2.2 | Activity 1. Development of new monitoring methods Purchase process of 4 mobile 3D birdradars reached contracting in september 2025 and radars are expected to be delivered in spring-summer 2026. Many other innovative monitoring devices (fieldwork rugged tablets, bat-detectors, bird sound recorders, thermal binoculars etc) testing by monitorers ended succsessfully and devices were purchased in bigger numbers to be integrated and used in national biodiversity monitoring programme. These devices will be also delivered in spring-summer 2026. Preparation of new innovative monitoring method basing on eDNA for monitoring invertebrates and fish in rivers was successfully finalised by contractor Estonian University of Life Sciences and results will be discussed further in January 2026. New monitoring method for testin was prepared for DNA basing monitoring of the Flying Squirrel as well as new method for Sand Lizzard and both methods testing is planned to be performed in 2026. Ten monitoring campaigns were successfully performed for volunteers and preparation of the results to be presented in feedback event in March 2026. Also 10 new voluntary bases monitoring campaigns were prepared for 2026.
2.3 | Activity 2. Development of IT systems Cooperation contract signed between Environment Agency and the IT Centre of the Ministry of the Environment (KEMIT) for IT developments foreseen in Component 1 Activity 2 to be performed during following two years (2026 and 2027). Preparatory work (data analysis, development meetings, IT-specifications etc) was done by Component 1 IT operators for following IT developments planned in 2026 and 2027: Automated cross-flow of data between the Environmental Monitoring Information System (KESE) and Estonian Nature Information System (EELIS); automated cross-flow of data between the eBiodiversity Portal (using online and citizen science based database called PlutoF) and Estonian Nature Information System (EELIS) - both these IT-developments are planned to be performed during 2026; development of a fieldwork tool that allows the field-workers to enter the monitoring and inventory data directly to the system as well as development of a management efficiency assessment tool for the Environmental Board into EELIS were planned to be developed during 2027.
Estimated cumulative physical progress (%)
Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board)
No | Short description of activities undertaken in the reporting period
3.1 | Management of the programme component The management cost includes expenses of the personnel (general project manager) and overheads of all other expenses on personnel (activities 1, 2 and 3). The project manager (0.5 FTEs) has been responsible for the overall coordination of the project, also hiring the personnel, organising meetings, seminars and study trips and dealing with financial reports. There has been one 5-day study trip to Switzerland for 8 people from the Environmental Board and 2 people from the Ministry of Climate. Swiss National Park, Jurapark Aargau, Zurich Canton and the Swiss Federal Institute for Forest, Snow and Landscape Research were vivisted during the study trip. Another study trip was to Brussels: two people participated in the seminar organised by the European Commission, the topic was connected with setting objectives in management plans.
3.2 | Activity 1: Conservation Management Effectiveness Assessment. The assessment of conservation management effectiveness started at the beginning of 2025. By the end of the year the management effectiveness of 97 sites has been assessed (the objective of the project is assessing 300 sites). The guidelines for the assessment has been reviewed according to the assessment results, gathering data has been made more effective (AI tools used). The assessing team: coordinator (1 FTE) and four assessors (2 FTEs). There is also one data analyst and one data specialist who support all the activities.
3.3 | Activity 2: Conservation Management Planning The guidelines for protected area management plans are finalized and ready for use. They include all compulsory (legally required) chapters, and several sections have been refined based on the testing process. During the testing phase, specialists prepared protected area management plans and provided feedback for improving or amending the guidelines, as a result of which the guidelines were further refined. In addition, the guidelines were supplemented with technical solutions such as visitor management online maps, the Environmental Portal webpage, and the full translation of the lists of pressures, threats, and conservation measures. Under the new guidelines, three (Anne loodusala, Kaasiku loodusala, Andresaare loodusala) management plans have been approved and twelve draft plans have been prepared for approval. The data sheet about protected areas was completed in 2025. The data sheet is based on the data analytics tool Tableau, and the information is displayed on the Environmental Portal (Keskkonnaportaal).
3.3 | The data used originate from the Estonian Nature Information System (EELIS). The web page has been publicly available since November 2025. Thanks to the web page, there is no longer a need to provide detailed descriptions or create maps for presenting the area and its values in management plans. The page consolidates all essential information related to protected areas in one place. 2025 was the year when most of the inventories of the habitats and species were prepared and ordered. The inventories give input to management plans. By the end of 2025 35 inventories were completed and 47 are being carried out. Three management plans of habitats have been prepared (lakes and springs, forests, wetlands). In June a seminar on river habitats took place, the seminar was organised together with Tartu University and Estonian Nature Fund, the number of participants was 117. The conservation management team: coordinator (1 FTE), 5 specialists (3 FTEs), 1 expert (0.4 FTEs), 1 expert (1 FTE) will join the team in February.
3.4 | Activity 3: Species Protection In January the kick-off seminar of changing the categories of protected species was organised, Estonian best species experts were invited to the seminar. 119 people participated in Tartu and more than 140 people listened to the seminar online. In 2025 8 meetings for experts were organised, 39 species experts took part of these meetings. 9 different species groups (239 protected species and a list of new species) were discussed. The 1st out of 3 planned proposals of changing the categories of protected species has been put together. 2 action plans for protected species (2 species) have been approved; 2 action plans have been prepared by experts (2 species), 10 action plans (for 141 species) are under preparation by experts (contracts have been signed). 4 species inventories have been completed and 7 are being carried out (contracts). The species team: coordinator (1 FTE), specialist (1 FTE), expert (1 FTE).
Estimated cumulative physical progress (%)
Note on A7: Please insert additional activities as needed; relate operational progress to the financial progress
Note on A15: Please insert additional activities as needed; relate physical progress to the financial progress
Note on A22: Please insert additional activities as needed; relate physical progress to the financial progress

## Programme Characteristics
Swiss-Estonian Cooperation Programme
Biodiversity Programme / Reimbursement Request No. 2
Programme Characteristics
To be filled in by Programme Operator | [9 empty] | To be filled in by Switzerland (see SAP characteristics) | [6 empty] | To be filled in by Switzerland (see SAP characteristics)
No | Programme Component Name | Swiss Contribution CHF | Specific Objective | Thematic Area | (in-country) Geographic Focus | Name Programme Component Operator | Type of entity | Planned duration |  | Sector 1 | Sector 2 (SDC only) | Sector 3 (SDC only) | PM Support RIO CC Adaptations | PM Support RIO CC mitigation | PM Support RIO CC desertification | PM Support Social Inlcusion | PM Gender | PM Governance | PM Disabilities | PM Digitalisation | PM Support RIO biodiversity
PSP/PA | maximum 40 characters | in CHF | according to Art. 2.2 Regulations | according to Art. 2.4 Regulations |  |  |  | Start | End | use title, not code | use title, not code | use title, not code
1 | Management Costs | 202953.63 | Environment and climate | Biodiversity | national coverage | Ministry of Climate | National administration | 2024-05-01 | 2028-08-31 | Bio-diversity |  |  | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Principal
2 | Programme Component 1 "Development of innovative monitoring technolo-gies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency) | 2883589.89 | Environment and climate | Biodiversity | national coverage | Estonian Environment Agency | National administration | 2024-05-01 | 2028-04-30 | Bio-diversity |  |  | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Significant | Principal
3 | Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board) | 3843456.11 | Environment and climate | Biodiversity | national coverage | Environmental Board | National administration | 2024-05-01 | 2028-04-30 | Biodiversity |  |  | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Not targeted | Principal
4 | Programme Component 3 | 0
5 | Programme Component 4 | 0
6 | Programme Component 5 | 0
7 | Programme Component 6 | 0
8 | Programme Component 7 | 0
9 | Programme Component 8 | 0
10 | Programme Component 9 | 0
delete or add lines as necessary
Note on A3: only to be completed and continuously updated for programmes
Note on A8: PSP / PA is internal number used in the CH Project management system.

## Procurement plan
Swiss-Estonian Cooperation Programme
Biodiversity Programme / Reimbursement Request No. 2
Procurement Plan
To be filled in by Programme Operator
Programme Component or Project Ref. No | Contract Name | If applicable, planned deadline for submitting documentation to Swiss "non objection" | Launch of tender planned | Tender notice will be submitted to Swiss side before publication | English translation of tender documents will be made available to bidders | Actual launch of tender (publication of tender notice) | Contract signature planned | Actual contract signature | Contract completion planned | Actual contract completion | Initially estimated costs |  | Actual costs based on signed contracts |  | Contractor | Expenditures incurred based on signed contracts |  | Comments
|  | quarter / year | quarter / year | yes/no | yes/no | date | quarter / year | date | quarter / year | date | EUR | CHF | EUR | CHF | name | EUR | CHF | status/ appeals/ cancelling or repetion of tender (incl. reason)/ numbers of bidders and rejected bids/risks/ irregularities related to the tender/ difficulties with the the Contractor/ suspension of works etc.
Programme Component 1 “Development of innovative monitoring technologies/solutions and improvement of Environmental databases and systems” | Purchasing mobile 3D bird radar | 2024 | 2024 | yes | yes | 2025-05-19 | 1Q/2025 | 2025-09-15 | 4Q/2025 | 2026-06-15 | 990000 | 955524 | 675400 | 651879.535 | Swiss Birdradar Solution AG |  |  | Costs wihtout VAT.
<
Note on A7: Provide an overview over all the procurements related to the SM. In case of Programmes, structure the table according to Programme Components. Unless otherwise agreed with Switzerland, only procurments above the threshold of CHF 150 000 must be listed. Insert a number. For related tenders use the same number and distinguish them using additional letters. For example, in case of a building renovation, there will be related tenders such as the technical project of the renovation (1a),the supervision of the renovation works (1b) and the renovation works (1c). The table is to be gradually updated and completed on a half-yearly basis.

## E-billing information
Deckblatt Rechnung E-Billing / Coversheet Invoice E-Billing
Buchungsinformationen / Booking information
Referenz-Nummer / Reference Number | REF-1006-66300
Projektnummer / Support Measure Identification Code | 7F-10768.01
Kreditorennummer / Creditor Number | 1000643543
Name des Kreditors / Creditor's name | Ministry of Finance of the Republic of Estonia
Strasse / Street | Suur-Ameerika 1
PLZ, Ort / Zip code and place | 10122 Tallinn
Währung / Currency: | CHF
Betrag / Reimbursement requested from Switzerland | 493819.05
Aufteilung nach Programmkomponente / Breakdown by programme component
Management Costs | 7244.39
Programme Component 1 "Development of innovative monitoring technolo-gies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency) | 146022.16
Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board) | 340552.5
Zahladresse / Account details
Kontoinhaber / bank account holder (if different from creditor name) | Ministry of Finance of the Republic of Estonia
IBAN-Nr.: | EE891010220034796011
SWIFT: | EEUHEE2X
Reference: | 2550081357
Bankbezeichnung / Name and address of the bank | SEB, Tornimäe 2, 15010 Tallinn, Estonia
Note on C5: The Reference Number, the Support Measure Identification Code and the Creditor Number are necessary for the e-billing in Switzerland. They will be provided by the Swiss side and remain the same throughout the implementation period.