## Budget
| Budget line | Detailed calculations explained | EST | NOR | costs
1 | Project management and auditing (October 2024-April 2025) |  | TOTAL: |  | 25735
| Project lead - TEEC | Project lead will work 16 hours per week with the wagefund of 25€/h (including taxes). There are 31 working weeks in 7 months (between 1.10.2024-30.04.2025). | 12400 |  | 16225
| Bookkeeping - TEEC | The bookkeepers are specialists who understand the financial requirements of project management. Meeting these requirements ensures the project's sustainability and cost-effectiveness, benefiting all target groups. Bookkeeping will work 3 hour per week with the wagefund of 25€/h (including taxes). | 2325
| External auditor | One time fee when reporting after the end of the project, price based on previous experience with a audit company. | 1500
| Project manager - FEE Norway | Project manager will work 3 hours per week with the wagefund of 65 €/h (31 working weeks). |  | 6045 | 9510
| Bookkeeping - FEE Norway | Bookkeeping will work 1 hour per week with the wagefund of 65€/h (31 working weeks). |  | 2015
| External auditor | One time fee when reporting after the end of the project, price based on previous experience with a audit company. |  | 1450
2 | Project kick-off meeting and training workshop in Oslo (28.-31.10.2024) |  | TOTAL: |  | 11431
| Most sustainable travel means | Tartu-Tallinn-Tartu bus round-ticket is 30 €/person, Tallinn-Stockholm-Tallinn ferry round-trip is 100 €/person, Stockholm-Oslo-Stockholm train round-ticket is 160 €/person. Room at the ferry for 3 is about 130 €, 2 rooms are needed. | 2000 |  | 5690
| Insurance | 6 people travelling for 4 days, optimal insurance to cover luggage loss or travel delays or trauma durig the travel is about 40 €/person. | 240
| Accommodation | 6 people accommodated in 3 twin rooms with the cost of 350 €/per room for 3 nights | 1050
| Daily allowance | 6 people traveling 4 days, 50 €/per day for each | 1200
| Organizer's and workshop facilitator's salary | 1 person from TEEC organizes the project meeting (buying tickets, booking accommodation, cooperating with Norwegian partners etc) with total of 24 hours work, and 2 people plan (10 hours each) and facilitate a workshop (2 hours) for Norwegian partners on how to run the Digital Cleanup Campaign. | 1200
| Study program/activity costs | Catering for all participants, pluss entrance to Climate house visitor centre, plus bus to school |  | 1500 | 5741
| Renting costs | 2 days rent of meeting room |  | 666
| Organizer's salary | 3 people from FEE Norway participates in work-shops and activities during the 2 day visit, plus 10 hours planning ahead of the meeting (7,5*3*2 hours + 10 hours planning = 55 hours). |  | 3575
3 | Developing the Digital Clean up Campaign and hosting a webinar for Norwegian teachers to participate (November2024-January 2025) |  | TOTAL: |  | 19550
| Specialist consultation | Sharing materials and best practices, consultation for Norwegian partners on how to run digital cleanup campaign and giving input for partner's developments from TEEC specialist (2 specialists are involved for 40 hours, 25€/h) | 2000 |  | 9000
| Developing learning materials | Experts for developing, adapting educational materials and tasks, translation Est-Nor (estimated 40 hours, 25€/h) | 2000
| Production of a campaign video | Short video for educational purpose and social media (bought in service) | 5000
| Developing and organizing | Develop guidelines and learning resources about the the topic, incl. slides, activity-cards (tasks), informative video and planning a webinar for all teachers (2 people x 40 hours). 2 people from FEE Norway plan and participated in the meetings, 2 x 5 hours (10 hours in total). |  | 5850 | 10550
| Specialist consultation | Bought in service, one time fee. Digital waste experts in the country. |  | 1000
| Communication services and production of learning materials | Bought in expert service to develop a plan for promoting this campaign, including the communication message and posters (NOK 30000). Create Social Media film (NOK 11000) = 3700€ |  | 3700
4 | Running the Digital Cleanup Campaign in Norway and in Estonia (January 2025) |  | TOTAL: |  | 6835
| Paid promotion | Promoting the campaign in social media, including cooperation with (green)influencer (bought in communication service). Estonian Digital Cleanup Campaign for 2025 has already got funds from the Estonian Environmental Investment Centre but we would like to add this as an enhancement for promotion to reach wider public and engage youth with the inclusion of a influencer. | 1500 |  | 1500
| Promoting the campaign | Arrange meetings with partners, municipalities and others to promote the campaign (2 people x 5 hours) |  | 650 | 5335
| Implement the webinar | The webinar will give a practial introduction to the topic and inspire the schools to particpate in the campagin (2 people x 2 hours) |  | 260
| Media coverage | NOK 15000 for promoting the campaign on social media (1400€) |  | 1400
| Implement communication activities | Post in social media, talk to journalists, publish newsletters and articles and send best practies to press departments in the municipalities where schools participate, etc. (1 person x 15 hours) |  | 975
| Evalution | Send survey to all participants to investigate both results (savings) and satisfaction with the campagin. Draw winners. (2 people x 5 hours) |  | 650
| Awards | Lump sum to 3 shools, drawn amongst participants (NOK 5000 x 3) to be used on Green Activities in the schools. |  | 1400
5 | Study trip to Norway/Trondheim - 10 Estonian Eco-School teachers to gather new connections and inspiration for a possible new Eco-Schools campaign “Enhancing the pollinators” to be introduced to Estonian schools (March or April 2025) |  | TOTAL: |  | 22450
| Most sustainable travel means | Tartu-Tallinn-Tartu bus round-ticket is 30 €/person, Tallinn-Stockholm-Tallinn ferry round-trip is 100 €/person, Stockholm-Oslo-Stockholm train round-ticket is 160 €/person. Room at the ferry for 2 is about 130 € (need 5 rooms), Oslo-Trondheim-Oslo train is ca 200 €/person (sleeping cabinet for 2 is used). | 7200 |  | 14300
| Insurance | 10 people travelling for 6 days, optimal insurance to cover luggage loss or travel delays or trauma durig the travel is about 40 €/person. | 400
| Accommodation | 10 people accommodated in 5 twin rooms with the cost of 300 EUR/per room for 2 nights | 1500
| Daily allowance | 10 people traveling 6 days, 50 EUR/per day for each | 3000
| Organizer's salary | 1 person to organize the trip from TEEC side (collaborate with partners, buying tickets etc), 5 full days to prepare, 6 days to travel along, wagefund is 25eur/h. | 2200
| Organiser's salary | 1 person x 30 hours (2 days travel and 2 day meetings) |  | 1950 | 8150
| Travel and accomodiaton costs | Norwegian partners to travel from Oslo to Trondheim |  | 900
| Program costs (catering, venue, workshop facilitation etc) | External facilitato from Trondheim municipality needs to be compensated (this includes renting costs, lectures, work-shops, visitor tickets and meals). Lunch and dinner for 12 people for 2,5 days (3 lunch and 2 dinners) (NOK 3*12*200 + NOK 2 x 12 x 450 = NOK 7200+ NOK 10800 = NOK 18000 |  | 5300
6 | Developing the "Pollinator Enhancement Campaign" for Estonia, hosting a webinar for Estonian teachers to introduce the new campaign and giving out starting packages for interested Eco-Schools (January-April 2025) |  | TOTAL: |  | 25175
| Production of study-kits | Disseminating pollinators/biodiversity enhancement study-kit (plants, seeds, study materials) in Estonia for at least in 50 schools, kindergartens. One of the schools will be Tartu Nature House to set a pilot garden. | 7500 |  | 22700
| Consulting with external experts | 5 days job for expert with wagefund of 35 €/h | 1400
| Developing learning materials | Translation costs, designing and printing the waterproof educational material/poster, total of 10 days job with wagefund 25 €/h. 10 days job for 2 people with wagefund of 25 €/h. After choosing and adaptinc sutable materials the TEEC specialist will work with experts and then order the thranslation and design of the materials. | 10800
| Campaign and webinar organizer's salary | Campaign and webinar to organize with 15 days job with wagefund of 25 €/h | 3000
| Buying and producing study-kits | Buying plants, seeds, educational materials for butterfly garden beds for attracting pollinators in Norway. The first 3 schools/kindergartens who register for partcipation in this spring pollinator campagin will receive a start package of relevant eqipment worth NOK 3000 |  | 850 | 2475
| Consultations with Tartu | Sharing experince and material from the Norwegian ongoing projects within these themes (1 person x 25 hours, wagefund of 65€/h) |  | 1625
7 | Communicating and disseminating project results in Estonia and Norway (October 2024-April 2025) |  | TOTAL: |  | 26575
| National dissemination event in Estonia | A climate mitigation and adaptation day at Tartu Nature House for families in April 2025. TEEC will oragnise a family event for 120 people to introduce the results of the project with hands-on methods (costs include organizers salary, 5 workshop facilitation and materials costs for buying plants, soil, 2 big and about 40 small info plates to showcase the pollinator friendly garden species and explain the solutions for public). | 5950 |  | 18350
| Communication | Communication specialist job to implement the dissemination part of the whole project (incl campaigns) so that each of our activity will have as long-lasting effects as possible. She will prepare comprehensive communication plan and strategies for the whole project period for the whole Estonian activities. She will work 16 hours per week with the wagefund of 25€/h. There are 31 working weeks between October 1, 2024, and April 30, 2025.Making it total of 16*31*23=11,408€ (including taxes). | 12400
| Communication | Communication specialist will work 1 hour per week for 31 weeks with the wagefund of 65€/h. |  | 2015 | 8225
| Norwegian dissemination event | Preparation and participation on conference for the Eco-Schools network at next National operators meeting or in annother international network channel (1 person x 4 hours). Renting conference meeting factilites and catering for national conferenc. |  | 2960
| Event organising, workshop or info stand facilitation | FEE Norway will arrange a national conference for all Eco-Schools coordinators where experiences and knowledge from this project is shared and promoted in the wider network (50 hours x 1 person) |  | 3250
8 | Overall expenses (7 % from the total project sum) |  | TOTAL: |  | 10368
| Overall expences - TEEC | 60% of the overall office expenses (heating, communications, work appliances etc) | 6220
| Overall expences - FEE Norway | 40% of the overall office expenses (heating, communications, work appliances etc) |  | 4148
|  |  | TOTAL PROJECT |  | 148119

## Activity Gantt chart
| 2024 |  |  | 2025
Detailed activity plan to be implemented after positive application round | 10 | 11 | 12 | 1 | 2 | 3 | 4 | Post-project
1. Project result-based management and coordination:
1.1. Open a new project in bookkeeping, notify project partners, hire a project manager and a communication specialist. Organize the project launching meeting in Oslo for the TEEC and FEE Norway staff to meet and develop detailed activity plans.
1.2. Manager, together with legal representative and bookkeeper prepares a project partnership contract between partners, and contract for the project manager. And keeps documented evidence throughout the project about its actions and results. Sign the contract, start implementation phase.
1.3. Calls for online meetings with partners to jointly plan and analyze project activities and impact.
1.4. Evaluation and risk assesment of the overall project results and cost-effectiveness of the budget use (reports). Develop a sustainability plan that outlines the specific actions and strategies to be implemented after the project ends. This plan includes timelines, responsibilities, and performance indicators.
1.5. Prepare joint project folders and tools to share with partners, prepares and adds necessary guidelines for project implementation (including signed tasks, budget, timeline, milestones, contacts, logos, dissemination plan, risk management methods, project quality assurance plan, quick communication channels)
1.6.. Assign compentent people for the development work (organizing events, facilitating workshops and communicating). Prepare and sign contracts with development team members. Keeping assosiated partners informed about our planned timeline, meeting times when we'd like to include them and implementation results.
1.7. Regularly reviews progress and adjust plans as needed to meet project goals and deadlines. Conducts project evaluation and analyzes project results against project goals and objectives, and sends reports to the funding facility to get the reimbursements for done expenditures. Writes project overviews and sends info to communication specialist for dissemination among target groups
1.8. Conducts project closeout activities, including final reporting, archiving project records, and conducting a lessons-learned session for the project team.
2. Activities
2.1. Organizing project kick-off meeting in Oslo between 28.-31.October 2024.
2.2. Developing, organizing and promoting the Digital Cleanup Campaign in Norway and Estonia from November 2024 till January 2025
2.3. Running the Digital Cleanup Campaign in Norway and Estonia in January 2025
2.4. Organizing a study visit for 10 Estonian Eco-School teachers to Trondheim, Norway in March or April 2025
2.5. Developing the "Pollinator Enhancement Campaign" for Estonia and Norway and hosting a webinar for Estonian teachers to introduce the new campaign
3. Communication and dissemination of the project results
3.1. Preparing comprehensive dissemination plan. Uploading project info to webpages and communicate to the public about launching this project.
3.2. Prepare, translate and target social media posts for stakeholders about our improvements, activities and findings from the project throughout the process. Ask our networks to share info.
3.3. Organizing and running a national dissemination event in each country.
3.4. Disseminate the project results through national online platforms and other possible channels to reach European and worldwide schools. Looking for opportunities to share information about project results on different national and international educational events (conferences, seminars, meetings, festivals etc). Explore opportunities to scale up or replicate successful project components in other communities or regions. Perhaps a new project with the same partner or some other organizations visited during the study trip. This can attract additional funding and support.