## Leht1
| Preliminary implementation schedule | 2024 | [7 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
|  | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
Activity
Programme level | Conclusion of the Support Measure Agreement | bar: 2024 May 1
Programme launching event | bar: 2024 May 1
Conclusion of the Support Measure Implementation Agreement | bar: 2024 Dec 8
Conditions for granting the support (Order by the Minister of Climate) | bar: 2025 Feb 10
Task Force meetings | bar: 2025 Jan 9; 2025 June 14; 2026 Jan 21; 2026 June 26; 2027 Jan 33; 2027 June 38; 2028 Jan 45
Steering Committee meetings | bar: 2024 Oct 6; 2025 Apr 12; 2026 Feb 22; 2027 Feb 34; 2028 Feb 46
Annual Support Measure Reports | bar: 2025 May 13 to 2025 July 15; 2026 May 25 to 2026 July 27; 2027 May 37 to 2027 July 39
Programme closing event | bar: 2028 March 47
Support Measure Completion Report | bar: 2028 May 49 to 2028 Oct 54
Programme Component 1 "Development of innovative monitoring technologies/solutions and improvement of Environmental data-bases and systems" (operator Environmental Agency)
Management | bar: 2024 May 1 to 2028 Apr 48
Development of new monitoring methods | bar: 2024 May 1 to 2028 Apr 48
Development of IT systems | bar: 2024 May 1 to 2028 Apr 48
Programme Component 2 “Implementation of a systematic assessment of the social and conservation outcomes of protected areas” (operator Environmental Board)
Management | bar: 2024 May 1 to 2028 Apr 48
Activity 1: Conservation Management Effectiveness Assessment | bar: 2024 Aug 4 to 2028 Apr 48
Activity 2: Conservation Management Planning | bar: 2024 May 1 to 2028 Apr 48
Activity 3: Species Protection | bar: 2024 May 1 to 2028 Apr 48