## Reimbursement Request
Swiss-Estonian Cooperation Programme
Reimbursement Request No. 5
Technical Assistance Fund
Instructions |  |  |  |  | Estonia
A. Basic information
Support Measure Title | Technical Assistance Fund
Support Measure Identification Code | Šveits.1.03 |  |  |  | 7F-10899.01
Support Measure duration | from | 2023-02-22 |  | to | 2029-12-03
Name of Executing Agency | State Shared Service Centre
Reporting period | from | 2026-01-01 |  | to | 2026-06-30
Reimbursement Request No | 5
Total Support Measure Budget (local currency) | 962075 |  |  | EUR
Maximum Swiss contribution (CHF) | 390000 |  | CHF
Swiss co-financing rate | on total budget |  | 42% | on total expenditures |  | 42%
Exchange rate used | CHF/EUR | 1.0656 |  | Date of exchange rate |  | 2026-09-01
B. Amount requested by the Paying Authority
Total amount requested | 45464.95 |  |  | EUR | 42664.31 | CHF
National co-financing | 26369.671 |  |  | EUR | 24745.3 | CHF
Deductions (according to Regulations 11.4/3) | 0 |  |  | EUR | 0 | CHF
Swiss co-financing = Reimbursement by CH | 19095.279 |  |  | EUR | 17919.01 | CHF
C. Available amount from the Swiss Contribution
Maximum Swiss Contribution | 390000 |  |  | CHF | 100%
Cumulative amount received from Switzerland | 77863.62 |  |  | CHF | 19.97%
Available amount before the current reimbursement | 312136.38 |  |  | CHF | 80.03%
Total amount of current reimbursement request | 17919.01 |  |  | CHF | 4.59%
Remaining amount after the current reimbursement | 294217.37 |  |  | CHF | 75.44%
D. Certification and approval of Reimbursement Request
National Coordination Unit
Name of the institution: | State Shared Service Centre
Address: | Lõkke 4, 10122 Tallinn
Name of the contact person: | Helena Musthallik
Position: | programme expert
Email: | helena.musthallik@rtk.ee
Phone number: | 3726466003
The National Coordination Unit hereby certifies
(i) that the Support Measure is implemented in accordance with the Technical Support Agreement; (ii) the reporting under Physical Progress, Financial Progress and Procurement Plan is true and accurate; (iii) that the reporting under Financial Progress reflects correctly the incurred expenditures; (iv) that recoverable VAT is not included in the Financial Progress as eligible expense; (v) that no double-financing occurs; (vi) that all procurements for which expenditures were incurred during the reporting period have been conducted in compliance with the applicable law of the Partner State and EU directives on public procurement; (vii) that the information and financial data provided in this Reimbursement Request has been thoroughly reviewed and found to be correct, reliable and accurate; (viii) that claimed expenditures are incurred as part of the Support Measure in accordance with the Framework Agreement and the Technical Support Agreement; (ix) that all payments declared have actually been made in the indicated (or exceptionally previous) reporting period; (x) the compliance with state aid rules of all activities performed in the reporting period.
Name: Urmo Merila | Position: | Deputy Director General
Date and signature | digitally signed
Paying Authority
Name of the institution: | State Shared Service Centre
Address: | Lõkke 4, 10122 Tallinn
Name of the contact person: | Janika Otsing
Position: | financial specialist
Email: | janika.otsing@rtk.ee
Phone number: | 3726631926
The Paying Authority hereby certifies
(i) to have checked the conformity of the Reimbursement Request with the financial stipulations, in particular the co-financing rate, set out in the Technical Support Agreement; (ii) to have received sufficient information for the certification of the Reimbursement Request; (iii) to have checked the compliance of the Reimbursement Request with the information available to the Paying Authority; (iv) that the co-financing of the Partner State has been provided in accordance with the Technical Support Agreement; (v) that based on the information available to the Paying Authority no double-financing could be identified; (vi) that recoverable VAT is not included in the Reimbursement Request as eligible expense.
The bank details for reimbursement are as follows:
Beneficiary: Ministry of Finance of the Republic of Estonia
IBAN: EE891010220034796011
SWIFT: EEUHEE2X
Reference: 2550081357
Name: Karin Viikmaa | Position: | Head of the Grants Payment Department
Date and signature | digitally signed
Note on A4: - Please fill out first the green fields in this sheet "Reimbursement Request" and only afterwards continue with the "Financial Progress" sheet and the other sheets - Indicate the number of the Reimbursement Request to get the data from the respective Reporting Period in the "Financial Progress" Sheet - In case of the last reimbursement request to be submitted to Switzerland, change the title to "Final Reimbursement Request" - Please note the comments with further instructions indicated by the red triangle in the cells - The sheet is protected without a password, to avoid unintentional deletion of a formula. You can press "unprotect sheet" to edit protected cells. - When submitting the Reimbursement Request to Switzerland, please send the signed version (e.g. PDF) as well as the Excel file. This sheet contains formulas to facilitate the preparation of the Reimbursement Request. It remains the responsibility of the Paying Authority to verify the correct calculations
Note on A10: please enter start and end date in the sheet "Financial Progress" in the respective column of the Reporting Period
Note on A11: Select a number between 1-14. According to your selection, the data from respective columns in the sheet "financial progress" Reporting Period will be gathered.
Note on A13: Please insert the amount as fixed in the Support Measure Agreement (Art 3 in SMA Template)
Note on A15: 1 CHF = amount in local currency This is the exchange rate from the sheet "Financial Progress" from the selected Reimbursement Request Number. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on B18: Value from sheet "Financial Progress". Ensure that the correct Reimbursement Request No is selected above.
Note on A20: The deducted amount of the financial correction in CHF should be calculated using the exchange rate applicable to the relevant Reimbursement Request to which the correction is linked. If the amount related to the irregularity was not included in any Reimbursement Request, the relevant exchange rate used in the Irregularity Report (immediate or regular) should be used. The total amount of deductions shall be entered here manually and further explained in the sheet "financial progress" "Information on deductions related to financial corrections (Art 11.4/3 Regulations)"
Note on A31: As the institutional set-up is country-specific, each partner state may adapt the certifications as appropriate in their specific institutional context and in line with the Regulations (namely Article 8.2).

## Financial Progress
Swiss-Estonian Cooperation Programme
Technical Assistance Fund / Reimbursement Request No. 5
Financial Progress
Instructions
[5 empty] | 1a | 1b | 1c | 1d | 2a | 2b | 2c | 2d | 3a | 3b | 3c | 3d | 4a | 4b | 4c | 4d | 5a | 5b | 5c | 5d | 6a | 6b | 6c | 6d | 7a | 7b | 7c | 7d | 8a | 8b | 8c | 8d | 9a | 9b | 9c | 9d | 10a | 10b | 10c | 10d | 11a | 11b | 11c | 11d | 12a | 12b | 12c | 12d | 13a | 13b | 13c | 13d | 14a | 14b | 14c | 14d
BUDGET |  |  |  |  | REPORTING PERIOD 1: |  | 2023-02-21 | 2024-06-30 | REPORTING PERIOD 2: |  | 2024-07-01 | 2024-12-31 | REPORTING PERIOD 3: |  | 2025-01-01 | 2025-06-30 | REPORTING PERIOD 4: |  | 2025-07-01 | 2025-12-31 | REPORTING PERIOD 5: |  | 2026-01-01 | 2026-06-30 | REPORTING PERIOD 6: |  | start date | end date | REPORTING PERIOD 7: |  | start date | end date | REPORTING PERIOD 8: |  | start date | end date | REPORTING PERIOD 9: |  | start date | end date | REPORTING PERIOD 10: |  | start date | end date | REPORTING PERIOD 11: |  | start date | end date | REPORTING PERIOD 12: |  | start date | end date | REPORTING PERIOD 13: |  | start date | end date | REPORTING PERIOD 14: |  | start date | end date | CUMULATIVE DATA | [6 empty] | PLANNING
|  | EUR | % | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR | CHF | CHF | CHF | EUR |  |  | CHF |  |  |  | CHF | CHF | CHF
No | Budget items | Budget 100% | Co-financing rate (CH co-financing) | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | Eligible expenditures 100% | National co-financing | Swiss contribution (co-financing) | Eligible expenditures 100% | % of Budget spent | Total remaining Budget | Eligible Expenditures 100% | Swiss contribution (co-financing) | % of Swiss Contribution spent | Total remaining Swiss contribution | Reimbursements expected to be received from Switzerland (current year) | Reimbursements expected to be received from Switzerland (year +1) | Reimbursements expected to be received from Switzerland (year +2)
| Exchange rate CHF/EUR | 1.0361 |  |  | 1.0684 |  |  |  | 1.0384 |  |  |  | 1.0702 |  |  |  | 1.1045 |  |  |  | 1.0656 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 2 |  |  |  | 1
1 | National Coordination Unit (NCU) | 626276 | 42% | 253875.83 | 60084.56 | 56239.15 | 32618.71 | 23620.44 | 25178.85 | 24247.23 | 14063.39 | 10183.84 | 28535.25 | 26663.34 | 15464.74 | 11198.6 | 30764.66 | 27854.32 | 16155.5 | 11698.82 | 33641.5 | 31569.18 | 18310.12 | 13259.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178204.82 | 28.45% | 448071.18 | 166573.22 | 69960.76 | 27.56% | 183915.07 | 0 | 30000 | 35000
1.1 | Meetings with the Swiss authorities, reg art 6.5 (a) | 57057 |  |  | 6478.31 |  |  |  | 1401.83 |  |  |  | 1844.64 |  |  |  | 4674 |  |  |  | 35.45 | [39 empty] | 14434.23 | 25.3% | 42622.77
1.2 | Information events, exchange of experience and capacity building between NCU, Paying Authority, Audit Authority, Executing Agencies, Intermediate Bodies, programme operators and programme component operators, reg art 6.5 (d) | 25280 | [58 empty] | 0 | 0% | 25280
1.3 | Expenditures associated with evaluations at the level of the CP or in a thematic area, reg art 6.5 (h) | 113969 | [58 empty] | 0 | 0% | 113969
1.4 | Visibility, public awareness of the CP, reg art 6.5 (j) | 124674 |  |  | 368.38 |  |  |  | 552.33 |  |  |  | 597.71 |  |  |  | 1123.34 |  |  |  | 9719.2 | [39 empty] | 12360.96 | 9.915% | 112313.04
1.5 | Translation and interpretation costs, reg art 6.5 (k) | 20338 | [58 empty] | 0 | 0% | 20338
1.6 | NCU salaries, social security contributions and other statutory costs in respect of public officials of the national entities, reg art 6.5 (m) | 284958 |  |  | 53237.87 |  |  |  | 23224.69 |  |  |  | 26092.9 |  |  |  | 24967.32 |  |  |  | 23886.85 | [39 empty] | 151409.63 | 53.13% | 133548.37
2 | Paying Authority | 86715 | 42% | 35151.98 | 0 | 0 | 0 | 0 | 5017.53 | 4831.88 | 2802.49 | 2029.39 | 6344.77 | 5928.55 | 3438.56 | 2489.99 | 6261.84 | 5669.47 | 3288.29 | 2381.18 | 5970.83 | 5603.03 | 3249.76 | 2353.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23594.97 | 27.21% | 63120.03 | 22032.93 | 9253.83 | 26.33% | 25898.15 | 0 | 5000 | 6000
2.1 | Paying Authority salaries, social security contributions and other statutory costs in respect of public officials of the national entities, reg art 6.5 (m) | 86715 | . | [5 empty] | 5017.53 |  |  |  | 6344.77 |  |  |  | 6261.84 |  |  |  | 5970.83 | [39 empty] | 23594.97 | 27.21% | 63120.03
2.2 | [60 empty] | 0 | #DIV/0! | 0
2.3 | [60 empty] | 0 | #DIV/0! | 0
2.4 | [60 empty] | 0 | #DIV/0! | 0
2.5 | [60 empty] | 0 | #DIV/0! | 0
3 | Audit Authority | 181739 | 42% | 73672.21 | 11404.95 | 10675.03 | 6191.52 | 4483.51 | 1863.67 | 1794.71 | 1040.93 | 753.78 | 3979.52 | 3718.46 | 2156.71 | 1561.75 | 7536.52 | 6823.57 | 3957.67 | 2865.9 | 5439.62 | 5104.54 | 2960.63 | 2143.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30224.28 | 16.63% | 151514.72 | 28116.31 | 11808.85 | 16.03% | 61863.36 | 0 | 6000 | 7000
3.1 | Audit Authority - Information events, exchange of experience and capacity building between NCU, Paying Authority, Audit Authority, Executing Agencies, Intermediate Bodies, programme operators and programme component operators, reg art 6.5 (d) | 2072 |  |  | 282.88 | [7 empty] | 55.88 |  |  |  | 30 |  |  |  | 41.52 | [39 empty] | 410.28 | 19.8% | 1661.72
3.2 | Audit Authority salaries, social security contributions and other statutory costs in respect of public officials of the national entities, reg art 6.5 (m) | 179667 |  |  | 11122.07 |  |  |  | 1863.67 |  |  |  | 3923.64 |  |  |  | 7506.52 |  |  |  | 5398.1 | [39 empty] | 29814 | 16.59% | 149853
3.3 | [60 empty] | 0 | #DIV/0! | 0
3.4 | [60 empty] | 0 | #DIV/0! | 0
3.5 | [60 empty] | 0 | #DIV/0! | 0
4 | Miscellaneous expenses | 67345 | 42% | 27299.89 | 8087.06 | 7569.49 | 4390.3 | 3179.19 | 1524.25 | 1467.86 | 851.36 | 616.5 | 1169.98 | 1093.23 | 634.08 | 459.15 | 898.25 | 813.28 | 471.7 | 341.58 | 413 | 387.56 | 224.79 | 162.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12092.54 | 17.96% | 55252.46 | 11331.42 | 4759.19 | 17.43% | 22540.7 | 0 | 2000 | 2000
4.1 | Miscellaneous expenses | 67345 |  |  | 8087.06 |  |  |  | 1524.25 |  |  |  | 1169.98 |  |  |  | 898.25 |  |  |  | 413 | [39 empty] | 12092.54 | 17.96% | 55252.46
4.2 | [60 empty] | 0 | #DIV/0! | 0
4.3 | [60 empty] | 0 | #DIV/0! | 0
4.4 | [60 empty] | 0 | #DIV/0! | 0
4.5 | [60 empty] | 0 | #DIV/0! | 0
5 | Programme Component 4 | 0 | 42% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 |  | 0 | 0
5.1 | [60 empty] | 0 | #DIV/0! | 0
5.2 | [60 empty] | 0 | #DIV/0! | 0
5.3 | [60 empty] | 0 | #DIV/0! | 0
5.4 | [60 empty] | 0 | #DIV/0! | 0
5.5 | [60 empty] | 0 | #DIV/0! | 0
6 | Programme Component 5 | 0 | 42% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
6.1 | [60 empty] | 0 | #DIV/0! | 0
6.2 | [60 empty] | 0 | #DIV/0! | 0
6.3 | [60 empty] | 0 | #DIV/0! | 0
6.4 | [60 empty] | 0 | #DIV/0! | 0
6.5 | [60 empty] | 0 | #DIV/0! | 0
7 | Programme Component 6 | 0 | 42% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
7.1 | [60 empty] | 0 | #DIV/0! | 0
7.2 | [60 empty] | 0 | #DIV/0! | 0
7.3 | [60 empty] | 0 | #DIV/0! | 0
7.4 | [60 empty] | 0 | #DIV/0! | 0
7.5 | [60 empty] | 0 | #DIV/0! | 0
8 | Programme Component 7 | 0 | 42% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
8.1 | [60 empty] | 0 | #DIV/0! | 0
8.2 | [60 empty] | 0 | #DIV/0! | 0
8.3 | [60 empty] | 0 | #DIV/0! | 0
8.4 | [60 empty] | 0 | #DIV/0! | 0
8.5 | [60 empty] | 0 | #DIV/0! | 0
9 | Programme Component 8 | 0 | 42% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
9.1 | [60 empty] | 0 | #DIV/0! | 0
9.2 | [60 empty] | 0 | #DIV/0! | 0
9.3 | [60 empty] | 0 | #DIV/0! | 0
9.4 | [60 empty] | 0 | #DIV/0! | 0
9.5 | [60 empty] | 0 | #DIV/0! | 0
10 | Programme Component 9 | 0 | 42% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0
10.1 | [60 empty] | 0 | #DIV/0! | 0
10.2 | [60 empty] | 0 | #DIV/0! | 0
10.3 | [60 empty] | 0 | #DIV/0! | 0
10.4 | [60 empty] | 0 | #DIV/0! | 0
10.5 | [60 empty] | 0 | #DIV/0! | 0
| TOTAL | 962075 | 42% | 389999.91 | 79576.57 | 74483.67 | 43200.53 | 31283.14 | 33584.3 | 32341.68 | 18758.17 | 13583.51 | 40029.52 | 37403.58 | 21694.09 | 15709.49 | 45461.27 | 41160.64 | 23873.16 | 17287.48 | 45464.95 | 42664.31 | 24745.3 | 17919.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244116.61 | 25.37% | 717958.39 | 228053.88 | 95782.63 | 24.56% | 294217.28 | 0 | 43000 | 50000
Information on modifications of the Support Measure approved during the reporting period According toTechnical Support Agreement Article 11
There were no modifications during the reporting period.
Information on non-eligible expenditures during the reporting period Please indicate the amount of non-eligible expenditures during the reporting period. Why are the expenditures non-eligible (for example due to irregularities or because it was agreed during the approval process of the SM that the costs are non-eligible)? Who will finance the non-eligible expenditures?
No ineligible costs were found.
Information on deductions related to financial corrections (Art 11.4/3 Regulations) In case of a financial correction already paid by Switzerland and deducted in this Reimbusement Request, please indicate the budget item, reporting period in question and provide explanation on the deduction made / refer to irregularity report.
There were no deductions.
Information on advance payments According to Art. 8.3. of the Regulations the Partner State may in exceptional cases agree with Switzerland on advance payments. If these are foreseen in the Support Measure Agreement, describe how the advance payment will be used in the upcoming reimbursement period and provide proof for the execution of the advance payment by the Partner State.
Advance payments were not foreseen.
Information regarding deviations from financial planning If there is a significant difference between the expenditures planned for this reporting period and the actual expenditures paid by the Paying Authority, justify the deviations. Also explain if the financial planning in this reimbursement request significantly differs from the financial planning in the previous reimbursement requests.If there is a cost overrun per budget item, describe how the additional costs will be covered.
There were no significant deviations.
Note on A4: - Please fill out first the green fields in this sheet "Reimbursement Request" and only afterwards continue with the "Financial Progress" sheet and the other sheets - Up to 14 Reimbursement Requests reporting periods are integrated in this sheet. Select the No in the "Reimbursement Request" sheet and use hide/unhide function to show the needed columns. - Dark grey cells can be left empty, green cells can be filled out. - Please note the comments with further instructions indicated by the red triangle in the cells - The sheet is protected without a password, to avoid unintentional deletion of a formula. This sheet contains formulas to facilitate the preparation of the Reimbursement Request. It remains the responsibility of the Paying Authority to verify the correct calculations.
Note on H6: insert start date of reporting period
Note on I6: insert end date of reporting period
Note on L6: insert start date of reporting period
Note on M6: insert end date of reporting period
Note on P6: insert start date of reporting period
Note on Q6: insert end date of reporting period
Note on T6: insert start date of reporting period
Note on U6: insert end date of reporting period
Note on X6: insert start date of reporting period
Note on Y6: insert end date of reporting period
Note on AB6: insert start date of reporting period
Note on AC6: insert end date of reporting period
Note on AF6: insert start date of reporting period
Note on AG6: insert end date of reporting period
Note on AJ6: insert start date of reporting period
Note on AK6: insert end date of reporting period
Note on AN6: insert start date of reporting period
Note on AO6: insert end date of reporting period
Note on AR6: insert start date of reporting period
Note on AS6: insert end date of reporting period
Note on AV6: insert start date of reporting period
Note on AW6: insert end date of reporting period
Note on AZ6: insert start date of reporting period
Note on BA6: insert end date of reporting period
Note on BD6: insert start date of reporting period
Note on BE6: insert end date of reporting period
Note on BH6: insert start date of reporting period
Note on BI6: insert end date of reporting period
Note on A8: Budget No should follow the same logic as indicated in the template, i.e. integer Numbers = main budget headings 1.1, 1.2, 1.3 etc = budget items Please use the same logic when adding additional budget headings / items
Note on B8: Budget items should be listed according to the budget in the Support Measure Agreement. If the budget in the Support Measure Agreement is amended, the budget in all Reimbursement Requests following the amendment shall be adapted accordingly. In case of Programmes, each Programme Component must be a separate budget heading item. The first budget heading is always the Programme Management. In case of the Support Measure Preparation Fund, preparation funds for each Support Measure should be listed as a separate budget item. In case of the Technical Assistance Fund, budget items to be structured according to the eligible tasks described in Art. 6.5 of the Regulations.
Note on BQ8: Please enter the amount that Switzerland is expected to contribute in the current and the next two calendar years. Please note that the Swiss reimbursements are always postponed by half a year compared to the payments. For the following year, for example, you must enter what Switzerland is expected to reimburse for the expenditures for the second half of the current year and the first semester of the following year.
Note on C9: 1 CHF = amount in local currency Please indicate the exchange rate as defined in the Budget of the Support Measure Agreement
Note on F9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on J9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on N9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on R9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on V9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on Z9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AD9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AH9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AL9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AP9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AT9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on AX9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on BB9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on BF9: 1 CHF = amount in local currency Insert here the exchange rate. The rate is defined by the Paying Authority according to Regulations Art 8.4 (i.e exchange rate of Partner State’s national bank effective on the last working day of the reimbursement period.)
Note on D10: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D17: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D23: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D29: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D35: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D41: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D47: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D53: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D59: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.
Note on D65: Insert here the co-financing rate of Switzerland for this component. In case the co-financing is on the Support Measure Level, insert the same co-financing rate for each component.

## Operational Progress
Swiss-Estonian Cooperation Programme
Technical Assistance Fund / Reimbursement Request No. 5
Operational Progress
National Coordination Unit (NCU)
No | Short description of activities undertaken in the reporting period
1.1 | Meetings with the Swiss authorities Annual Meeting of the Swiss-Estonian Cooperation Programme On 1 June 2026, the NCU organised the third Annual Meeting of the Cooperation Programme, which was held at the Joint Building of Ministries in Tallinn. During the meeting, the Annual Cooperation Programme Report for the previous year was discussed and approved.
1.1 | Steering Committee meetings The programme expert from the NCU participated in the following meetings of the SM Steering Committees: the Steering Committee meeting of the SM “Biodiversity Programme”, held on 27-28 April 2026 in Tartumaa; the Steering Committee meeting of the SM “Supporting Social Inclusion”, held on 05 March 2026 in Pärnu.
1.1 | Other meetings and events On 31 May 2026, the NCU organised an Evening Gathering at the Tallinn Zoo. The event was attended by representatives of Switzerland, the SCO, the NCU, Programme Operators, Programme Component Operators, Implementers and the Audit Authority. The event provided participants with an opportunity to meet and interact in an informal atmosphere.
1.4 | Visibility,public awareness The NCU published information about the Cooperation Programme on the website of the State Shared Service Centre and organised discussions and meetings related to communication. In spring 2026, the NCU promoted videos about the Cooperation Programme, filmed in 2025, through paid Facebook posts. Videos are also publicly available on YouTube and on the NCU website. On 5 February and on 21 May 2026, joint communication meetings were held with the participation of the NCU programme operators, component operators and implementers. Future communication activities and communication-related issues were discussed during the meetings.
1.6 | NCU salaries The NCU supports Programme Operators, Component Operators, Implementers and Partners in the implementation of their activities. The NCU programme expert participated in the Task Force and Steering Committee meetings of both Support Measures and organised the Annual Meeting, communication meetings and regular meetings of the programme components, involving Programme Operators, Component Operators, Implementers and Partners. The programme expert reviewed the Annual Support Measure Reports and Reimbursement Requests submited by the Programme Operators and prepared the Reimbursement Requests for Technical Assistance. The programme expert prepared the Annual Cooperation Programme Report and submitted it to the SCO in April 2026. The report was subsequently approved at the Annual Meeting held in June 2026.
Estimated cumulative physical progress (%)
Paying Authority
No | Short description of activities undertaken in the reporting period
2.1 | Paying Authority salaries In March 2026, the Paying Authority submitted to the SCO Reimbursement Request No. 4 for Technical Assistance and Reimbursement Request No. 2 for each of the Support Measures, “Supporting Social Inclusion” and “Biodiversity Programme”, covering the period from 1 July 2025 to 31 December 2025.
Estimated cumulative physical progress (%)
Audit Authority
No | Short description of activities undertaken in the reporting period
3.1 | Audit Authority - Information events, exchange of experience and capacity building A representative of the Audit Authority participated in the Annual Conference on Risk Management and Internal Control in April 2026.
3.2 | Audit Authority salaries The Audit Authority carried out an audit of the expenditures paid by the NCU during the period from 1 July 2024 to 30 June 2025. The Audit Authority prepared the Annual Audit Report, which was submitted to the SCO in April 2026. A representative of the Audit Authority participated in the Annual Meeting and provided an overview of the Audit Authority’s activities.
Estimated cumulative physical progress (%)
Miscellaneous expenses
No | Short description of activities undertaken in the reporting period
4.1 | Miscellaneous expenses Expenditures of costs of paid promotion on Facebook, Dokobit package for submitting Reimbursement Requests.
Estimated cumulative physical progress (%)
Note on A7: Please insert additional activities as needed; relate operational progress to the financial progress
Note on A16: Please insert additional activities as needed; relate operational progress to the financial progress
Note on A21: Please insert additional activities as needed; relate operational progress to the financial progress
Note on A27: Please insert additional activities as needed; relate operational progress to the financial progress

## Programme Characteristics
Swiss-Estonian Cooperation Programme
Technical Assistance Fund / Reimbursement Request No. 5
Programme Characteristics
To be filled in by Programme Operator | [9 empty] | To be filled in by Switzerland (see SAP characteristics) | [6 empty] | To be filled in by Switzerland (see SAP characteristics)
No | Programme Component Name | Swiss Contribution CHF | Specific Objective | Thematic Area | (in-country) Geographic Focus | Name Programme Component Operator | Type of entity | Planned duration |  | Sector 1 | Sector 2 (SDC only) | Sector 3 (SDC only) | PM Support RIO CC Adaptations | PM Support RIO CC mitigation | PM Support RIO CC desertification | PM Support Social Inlcusion | PM Gender | PM Governance | PM Disabilities | PM Digitalisation | PM Support RIO biodiversity
PSP/PA | maximum 40 characters | in CHF | according to Art. 2.2 Regulations | according to Art. 2.4 Regulations |  |  |  | Start | End | use title, not code | use title, not code | use title, not code
1 | National Coordination Unit (NCU) | 253875.83
2 | Paying Authority | 35151.98
3 | Audit Authority | 73672.21
4 | Miscellaneous expenses | 27299.89
5 | Programme Component 4 | 0
6 | Programme Component 5 | 0
7 | Programme Component 6 | 0
8 | Programme Component 7 | 0
9 | Programme Component 8 | 0
10 | Programme Component 9 | 0
delete or add lines as necessary
Note on A3: only to be completed and continuously updated for programmes
Note on A8: PSP / PA is internal number used in the CH Project management system.

## Procurement plan
Swiss-Estonian Cooperation Programme
Technical Assistance Fund / Reimbursement Request No. 5
Procurement Plan
To be filled in by Programme Operator
Programme Component or Project Ref. No | Contract Name | If applicable, planned deadline for submitting documentation to Swiss "non objection" | Launch of tender planned | Tender notice will be submitted to Swiss side before publication | English translation of tender documents will be made available to bidders | Actual launch of tender (publication of tender notice) | Contract signature planned | Actual contract signature | Contract completion planned | Actual contract completion | Initially estimated costs |  | Actual costs based on signed contracts |  | Contractor | Expenditures incurred based on signed contracts |  | Comments
|  | quarter / year | quarter / year | yes/no | yes/no | date | quarter / year | date | quarter / year | date | EUR | CHF | EUR | CHF | name | EUR | CHF | status/ appeals/ cancelling or repetion of tender (incl. reason)/ numbers of bidders and rejected bids/risks/ irregularities related to the tender/ difficulties with the the Contractor/ suspension of works etc.
| Evaluation of SMs "Supporting Social Inclusion" and "Biodiversity Programme" according to Regulation Article 10.3 p. 2 |  | IV/2027 |  |  |  | I/2028 |  | III/2028 | EUR: 113968.91; CHF: 110000
<
Note on A7: Provide an overview over all the procurements related to the SM. In case of Programmes, structure the table according to Programme Components. Unless otherwise agreed with Switzerland, only procurments above the threshold of CHF 150 000 must be listed. Insert a number. For related tenders use the same number and distinguish them using additional letters. For example, in case of a building renovation, there will be related tenders such as the technical project of the renovation (1a),the supervision of the renovation works (1b) and the renovation works (1c). The table is to be gradually updated and completed on a half-yearly basis.

## E-billing information
Deckblatt Rechnung E-Billing / Coversheet Invoice E-Billing
Buchungsinformationen / Booking information
Referenz-Nummer / Reference Number | REF-1006-66300
Projektnummer / Support Measure Identification Code | 7F-10899.01
Kreditorennummer / Creditor Number | 1000643543
Name des Kreditors / Creditor's name | Ministry of Finance of the Republic of Estonia
Strasse / Street | Suur-Ameerika 1
PLZ, Ort / Zip code and place | 10122 Tallinn
Währung / Currency: | CHF
Betrag / Reimbursement requested from Switzerland | 17919.01
Aufteilung nach Programmkomponente / Breakdown by programme component
National Coordination Unit (NCU) | 13259.06
Paying Authority | 2353.27
Audit Authority | 2143.91
Miscellaneous expenses | 162.77
Zahladresse / Account details
Kontoinhaber / bank account holder (if different from creditor name) | Ministry of Finance of the Republic of Estonia
IBAN-Nr.: | EE891010220034796011
SWIFT: | EEUHEE2X
Referenz-Nummer / Reference Number | 2550081357
Bankbezeichnung / Name and address of the bank | SEB, Tornimäe 2, 15010 Tallinn, Estonia
Note on C5: The Reference Number, the Support Measure Identification Code and the Creditor Number are necessary for the e-billing in Switzerland. They will be provided by the Swiss side and remain the same throughout the implementation period.